## REPORT HASIL
WO PRODUCTION CUTTING
Co Date vs Fabric Receipt in Cutting Date | [8 empty] | Start Cutting Date vs PPIC Date | [8 empty] | Lebar Kain Plan vs Lebar Kain Actual | [8 empty] | Consumption Plan vs Consumption Actual | [7 empty] | Garment Short/Over (Pcs) | [6 empty] | Sisa Fabric
WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE
182195 | ADIDAS | GM2 | 292099 | RESTY HERMA ROSTANIKA | 01-Mar-24 |  | -3 | KAIN MSH DI CLN | 181985 | ADIDAS | GM1 | 292578 | PUTRI EGA ANJELIA | 06-Mar-24 |  | 2 |  | 181982 | ADIDAS | GM1 | 292578 | SUMIATI | 58 | 53.4 | -7.97 |  | 181982 | ADIDAS | GM1 | 292578 | PUTRI EGA ANJELIA | 0.413 | 0.3753 | -9.13 | 182174 | ADIDAS | GM1 | 292103 | PUTRI EGA ANJELIA | -2.84 | 12 April | 181983 | ADIDAS | GM1 | 292583 | PUTRI EGA ANJELIA | 2.95 | 22 March
182175 | ADIDAS | GM1 | 292105 | PUTRI EGA ANJELIA | 01-Mar-24 |  | -3 | KAIN MSH DI CLN | 181985 | ADIDAS | GM1 | 292585 | PUTRI EGA ANJELIA | 06-Mar-24 |  | 2 |  | 181852 | TOYOTA | CNJ2 | 292195 |  | 56 | 55 | -1.79 |  | 181982 | ADIDAS | GM1 | 292582 | PUTRI EGA ANJELIA | 0.413 | 0.4053 | -1.86 | 182090 | KAZEN-S# | CNJ2 | 247754 | SRI SETIASIH | 17.85 | 01 June | 182165 | ADIDAS | GM1 | 292593 | PUTRI EGA ANJELIA | 3.66 | 28 March
182176 | ADIDAS | GM1 | 292105 | PUTRI EGA ANJELIA | 01-Mar-24 |  | -3 | KAIN MASIH DI CLN | 181984 | ADIDAS | GM1 | 292584 | PUTRI EGA ANJELIA | 06-Mar-24 |  | 2 |  | 182164 | ADIDAS | GM1 | 292593 | SUMIATI | 70 | 70.9 | 1.29 |  | 181983 | ADIDAS | GM1 | 292583 | PUTRI EGA ANJELIA | 0.396 | 0.3887 | -1.84 | [7 empty] | 182090 | KAZEN-S# | CNJ2 | 247754 | SRI SETIASIH | 3.73 | 01 June
182174 | ADIDAS | GM1 | 292103 | PUTRI EGA ANJELIA | 01-Mar-24 |  | -3 |  | 181984 | ADIDAS | GM1 | 292582 | PUTRI EGA ANJELIA | 06-Mar-24 |  | 2 |  | 181982 | ADIDAS | GM1 | 292582 | SUMIATI | 58 | 59 | 1.72 |  | 181983 | ADIDAS | GM1 | 292584 | PUTRI EGA ANJELIA | 0.396 | 0.3891 | -1.74 | [7 empty] | 181983 | ADIDAS | GM1 | 292582 | PUTRI EGA ANJELIA | 4.86 | 22 March
182172 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 01-Mar-24 |  | -3 |  | 181985 | ADIDAS | GM1 | 292582 | PUTRI EGA ANJELIA | 06-Mar-24 |  | 2 |  | 181983 | ADIDAS | GM1 | 292583 | SUMIATI | 58 | 59 | 1.72 |  | 181983 | ADIDAS | GM1 | 292582 | PUTRI EGA ANJELIA | 0.396 | 0.3894 | -1.67 | [7 empty] | 181983 | ADIDAS | GM1 | 292584 | PUTRI EGA ANJELIA | 5.76 | 22 March
182174 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 01-Mar-24 |  | -3 |  | 181984 | ADIDAS | GM1 | 292583 | PUTRI EGA ANJELIA | 06-Mar-24 |  | 2 |  | 181983 | ADIDAS | GM1 | 292584 | SUMIATI | 58 | 59 | 1.72 |  | 181852 | TOYOTA | CNJ2 | 292195 | SRI SETIASIH | 1.2537 | 1.2378 | -1.27 | [7 empty] | 181982 | ADIDAS | GM1 | 292578 | PUTRI EGA ANJELIA | 6.76 | 22 March
182173 | ADIDAS | GM1 | 292102 | PUTRI EGA ANJELIA | 01-Mar-24 |  | -3 | KAIN MSH DI CLN | 182181 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 07-Mar-24 |  | 3 |  | 181983 | ADIDAS | GM1 | 292582 | SUMIATI | 58 | 59 | 1.72 |  | 182178 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.285 | 0.2827 | -0.81 | [7 empty] | 181978 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 9.95 | 15 March
182195 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 01-Mar-24 |  | -3 | KAIN MSH DI CLN | 182181 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 07-Mar-24 |  | 3 |  | 181976 | ADIDAS | GM2 | 292586 | SUMIATI | 60 | 62 | 3.33 |  | 182090 | KAZEN-S# | CNJ2 | 247754 | SRI SETIASIH | 0.9007 | 0.8957 | -0.56 | [7 empty] | 181852 | TOYOTA | CNJ2 | 292195 | SRI SETIASIH | 10.1 | 03 June
182175 | ADIDAS | GM1 | 292104 | PUTRI EGA ANJELIA | 01-Mar-24 |  | -3 | KAIN MSH DI CLN | 182181 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 07-Mar-24 |  | 3 |  | 181978 | ADIDAS | GM2 | 292586 | SUMIATI | 60 | 62.5 | 4.17 |  | 182197 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 0.333 | 0.3318 | -0.36 | [7 empty] | 182178 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 10.54 | 12 April
182176 | ADIDAS | GM1 | 292104 | PUTRI EGA ANJELIA | 01-Mar-24 |  | -3 | KAIN MSH DI CLN | 182172 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 08-Mar-24 |  | 4 |  | 181984 | ADIDAS | GM1 | 292583 | SUMIATI | 58 |  |  |  | 181976 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 0.0983 | 0.1025 | 4.27 | [7 empty] | 182164 | ADIDAS | GM1 | 292593 | PUTRI EGA ANJELIA | 15.37 | 28 March
182157 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 01-Mar-24 |  | -3 |  | 182172 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 08-Mar-24 |  | 4 |  | 181984 | ADIDAS | GM1 | 292584 | SUMIATI | 58 |  |  |  | 181978 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 0.0413 | 0.0447 | 8.23 | [7 empty] | 181976 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 18.27 | 15 March
182158 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 01-Mar-24 |  | -3 |  | 182172 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 08-Mar-24 |  | 4 |  | 181984 | ADIDAS | GM1 | 292582 | SUMIATI | 58 |  |  |  | 182164 | ADIDAS | GM1 | 292593 | PUTRI EGA ANJELIA | 0.1279 | 0.1825 | 42.69 | [7 empty] | 181982 | ADIDAS | GM1 | 292582 | PUTRI EGA ANJELIA | 20.07 | 22 March
182159 | ADIDAS | GM2 | 292590 | RESTY HERMA ROSTANIKA | 01-Mar-24 |  | -3 |  | 182085 | KAZEN-S# | CNJ2 | 247749 | SRI SETIASIH | 10-Mar-24 |  | 6 | KAIN OK, | 181985 | ADIDAS | GM1 | 292585 | SUMIATI | 58
182160 | ADIDAS | GM2 | 292590 | RESTY HERMA ROSTANIKA | 01-Mar-24 |  | -3 |  | 182180 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 14-Mar-24 |  | 10 |  | 181985 | ADIDAS | GM1 | 292578 | SUMIATI | 58
182159 | ADIDAS | GM2 | 292587 | RESTY HERMA ROSTANIKA | 01-Mar-24 |  | -3 |  | 181986 | ADIDAS | GM1 | 292578 | PUTRI EGA ANJELIA | 17-Mar-24 |  | 13 |  | 181985 | ADIDAS | GM1 | 292582 | SUMIATI | 58
182160 | ADIDAS | GM2 | 292587 | RESTY HERMA ROSTANIKA | 01-Mar-24 |  | -3 |  | 181986 | ADIDAS | GM1 | 292585 | PUTRI EGA ANJELIA | 17-Mar-24 |  | 13 |  | 181986 | ADIDAS | GM1 | 292585 | SUMIATI | 58
182159 | ADIDAS | GM2 | 292589 | RESTY HERMA ROSTANIKA | 01-Mar-24 |  | -3 |  | 181986 | ADIDAS | GM1 | 292582 | PUTRI EGA ANJELIA | 17-Mar-24 |  | 13 |  | 181986 | ADIDAS | GM1 | 292578 | SUMIATI | 58
182160 | ADIDAS | GM2 | 292589 | RESTY HERMA ROSTANIKA | 01-Mar-24 |  | -3 |  | 182171 | ADIDAS | GM1 | 267375 | PUTRI EGA ANJELIA | 21-Mar-24 |  | 17 |  | 181986 | ADIDAS | GM1 | 292582 | SUMIATI | 58
182139 | ADIDAS | GK | 290059 | TRI LESTARI | 04-Mar-24 |  | 0 |  | 182195 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 31-Mar-24 |  | 27 |  | 182171 | ADIDAS | GM1 | 267375 | SUMIATI | 70
182181 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 04-Mar-24 |  | 0 |  | 182195 | ADIDAS | GM2 | 292099 | RESTY HERMA ROSTANIKA | 31-Mar-24 |  | 27 | KAIN MSH DI CLN | 182179 | ADIDAS | GM2 | 290059 | SUMIATI | 58
182139 | ADIDAS | GK | 290060 | TRI LESTARI | 04-Mar-24 |  | 0 |  | 182195 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 31-Mar-24 |  | 27 | KAIN MSH DI CLN | 182157 | ADIDAS | GM2 | 292586 |  | 60
182139 | ADIDAS | GK | 290064 | TRI LESTARI | 04-Mar-24 |  | 0 |  | 182193 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 12-Apr-24 |  | 39 |  | 182158 | ADIDAS | GM2 | 292586 |  | 60
182085 | KAZEN-S# | CNJ2 | 247749 | SRI SETIASIH | 04-Mar-24 |  | 0 | KAIN OK, | 182157 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 15-Apr-24 |  | 42 |  | 182159 | ADIDAS | GM2 | 292589 |  | 60
[9 empty] | 182138 | ADIDAS | GK | 290059 | TRI LESTARI | 19-Apr-24 |  | 46 |  | 182159 | ADIDAS | GM2 | 292587 |  | 60
[9 empty] | 182138 | ADIDAS | GK | 290060 | TRI LESTARI | 19-Apr-24 |  | 46 |  | 182159 | ADIDAS | GM2 | 292590 |  | 60
[9 empty] | 182138 | ADIDAS | GK | 290064 | TRI LESTARI | 19-Apr-24 |  | 46 |  | 182160 | ADIDAS | GM2 | 292589 |  | 60
[9 empty] | 182158 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 22-Apr-24 |  | 49 |  | 182160 | ADIDAS | GM2 | 292587 |  | 60
[9 empty] | 182179 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 25-Apr-24 |  | 52 |  | 182160 | ADIDAS | GM2 | 292590 |  | 60
[9 empty] | 182194 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 26-Apr-24 |  | 53 |  | 182172 | ADIDAS | GM1 | 290059 | SUMIATI | 58
[9 empty] | 182159 | ADIDAS | GM2 | 292590 | RESTY HERMA ROSTANIKA | 26-Apr-24 |  | 53 |  | 182172 | ADIDAS | GM1 | 290060 | SUMIATI | 58
[9 empty] | 182159 | ADIDAS | GM2 | 292587 | RESTY HERMA ROSTANIKA | 26-Apr-24 |  | 53 |  | 182172 | ADIDAS | GM1 | 290061 | SUMIATI | 58
[9 empty] | 182159 | ADIDAS | GM2 | 292589 | RESTY HERMA ROSTANIKA | 26-Apr-24 |  | 53 |  | 182173 | ADIDAS | GM1 | 292102 | SUMIATI | 58
[9 empty] | 182160 | ADIDAS | GM2 | 292590 | RESTY HERMA ROSTANIKA | 30-Apr-24 |  | 57 |  | 182173 | ADIDAS | GM1 | 290059 | SUMIATI | 58
[9 empty] | 182160 | ADIDAS | GM2 | 292587 | RESTY HERMA ROSTANIKA | 30-Apr-24 |  | 57 |  | 182173 | ADIDAS | GM1 | 290060 | SUMIATI | 58
[9 empty] | 182160 | ADIDAS | GM2 | 292589 | RESTY HERMA ROSTANIKA | 30-Apr-24 |  | 57 |  | 182174 | ADIDAS | GM1 | 290063 | SUMIATI | 58
[9 empty] | 182139 | ADIDAS | GK | 290059 | TRI LESTARI | 30-Apr-24 |  | 57 |  | 182174 | ADIDAS | GM1 | 290061 | SUMIATI | 58
[9 empty] | 182139 | ADIDAS | GK | 290060 | TRI LESTARI | 30-Apr-24 |  | 57 |  | 182174 | ADIDAS | GM1 | 292103 | SUMIATI | 58
[9 empty] | 182139 | ADIDAS | GK | 290064 | TRI LESTARI | 30-Apr-24 |  | 57 |  | 182175 | ADIDAS | GM1 | 292104 | SUMIATI | 58
[9 empty] | 182173 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA |  |  |  |  | 182175 | ADIDAS | GM1 | 292105 | SUMIATI | 58
[9 empty] | 182174 | ADIDAS | GM1 | 290063 | PUTRI EGA ANJELIA |  |  |  |  | 182175 | ADIDAS | GM1 | 290060 | SUMIATI | 58
[9 empty] | 182173 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA |  |  |  |  | 182176 | ADIDAS | GM1 | 292104 | SUMIATI | 58
[9 empty] | 182175 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA |  |  |  |  | 182176 | ADIDAS | GM1 | 292105 | SUMIATI | 58
[9 empty] | 182176 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA |  |  |  |  | 182176 | ADIDAS | GM1 | 290060 | SUMIATI | 58
[9 empty] | 182175 | ADIDAS | GM1 | 292105 | PUTRI EGA ANJELIA |  |  |  | KAIN MSH DI CLN | 182194 | ADIDAS | GM2 | 290059 |  | 58
[9 empty] | 182176 | ADIDAS | GM1 | 292105 | PUTRI EGA ANJELIA |  |  |  | KAIN MASIH DI CLN | 182195 | ADIDAS | GM2 | 292099 | SUMIATI | 58
[9 empty] | 182174 | ADIDAS | GM1 | 292103 | PUTRI EGA ANJELIA |  |  |  |  | 182195 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[9 empty] | 182174 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA |  |  |  |  | 182195 | ADIDAS | GM2 | 290060 | SUMIATI | 58
[9 empty] | 182173 | ADIDAS | GM1 | 292102 | PUTRI EGA ANJELIA |  |  |  | KAIN MSH DI CLN | 182138 | ADIDAS | GK | 290064 |  | 58
[9 empty] | 182175 | ADIDAS | GM1 | 292104 | PUTRI EGA ANJELIA |  |  |  | KAIN MSH DI CLN | 182138 | ADIDAS | GK | 290060 |  | 58
[9 empty] | 182176 | ADIDAS | GM1 | 292104 | PUTRI EGA ANJELIA |  |  |  | KAIN MSH DI CLN | 182138 | ADIDAS | GK | 290059 |  | 58
[18 empty] | 182193 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[18 empty] | 182085 | KAZEN-S# | CNJ2 | 247749 | GITA | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 182180 | ADIDAS | GM1 | 290059 | SUMIATI | 58
[18 empty] | 182181 | ADIDAS | GM1 | 290059 | SUMIATI | 58
[18 empty] | 182181 | ADIDAS | GM1 | 290060 | SUMIATI | 58
[18 empty] | 182181 | ADIDAS | GM1 | 290061 | SUMIATI | 58
[18 empty] | 182139 | ADIDAS | GK | 290064 |  | 58
[18 empty] | 182139 | ADIDAS | GK | 290060 |  | 58
[18 empty] | 182139 | ADIDAS | GK | 290059 |  | 58