## REPORT HASIL
Co Date vs Fabric Receipt in Cutting Date | [8 empty] | Start Cutting Date vs PPIC Date | [8 empty] | Lebar Kain Plan vs Lebar Kain Actual | [8 empty] | Consumption Plan vs Consumption Actual | [7 empty] | Garment Short/Over (Pcs) | [6 empty] | Sisa Fabric
WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE
181634 | ADIDAS | GM2 | 292107 | RESTY HERMA ROSTANIKA | 29-Dec-23 |  | -7 | KAIN BELUM DATANG, ESTIMASI 03 JANUARI 2024 | 181592 | ADIDAS | GM1 | 295031 | PUTRI EGA ANJELIA | 20-Dec-23 |  | -16 | KONTRAK BLM RELEASE | 181629 | ADIDAS | GM2 | 290060 | SUMIATI | 58 | 58 | 0 |  | 181584 | ADIDAS | GK | 290059 | TRI LESTARI | 0.411 | 0.4106 | -0.1 | 181648 | COCOS-S# | CBA | 269390 |  | -39.34 | 15 February | 181583 | ADIDAS | GK | 290059 | TRI LESTARI | 0.82 | 16 February
181634 | ADIDAS | GM2 | 293262 | RESTY HERMA ROSTANIKA | 29-Dec-23 |  | -7 | KAIN BELUM DATANG, ESTIMASI 03 JANUARI 2024 | 181592 | ADIDAS | GM1 | 295030 | PUTRI EGA ANJELIA | 20-Dec-23 |  | -16 | KONTRAK BLM RELEASE | 181629 | ADIDAS | GM2 | 292100 | SUMIATI | 58 | 58 | 0 |  | 181629 | ADIDAS | GM2 | 292100 | RESTY HERMA ROSTANIKA | 0.201 | 0.2017 | 0.35 | 181629 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | -25.54 | 16 February | 181634 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 3.73 | 16 February
181629 | ADIDAS | GM2 | 294353 | RESTY HERMA ROSTANIKA | 29-Dec-23 |  | -7 | KAIN BELUM DATANG, ESTIMASI 03 JANUARI 2024 | 181594 | ADIDAS | GM1 | 295032 | PUTRI EGA ANJELIA | 26-Dec-23 |  | -10 | KAIN BELUM DATANG, ESTIMASI 05 JANUARI 2024 | 181629 | ADIDAS | GM2 | 290059 | SUMIATI | 58 | 58 | 0 |  | 181629 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.201 | 0.2017 | 0.35 | 181648 | COCOS-S# | CBA | 269388 |  | -11.76 | 15 February | 181587 | ADIDAS | GK | 290059 | TRI LESTARI | 3.82 | 16 February
181602 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181594 | ADIDAS | GM1 | 295033 | PUTRI EGA ANJELIA | 26-Dec-23 |  | -10 | KAIN BELUM DATANG, ESTIMASI 05 JANUARI 2024 | 181634 | ADIDAS | GM2 | 290059 | SUMIATI | 58 | 58 | 0 |  | 181634 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.186 | 0.1867 | 0.38 | 181648 | COCOS-S# | CBA | 269389 |  | -0.61 | 15 February | 181629 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 4.17 | 16 February
181603 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181595 | ADIDAS | GM1 | 267375 | PUTRI EGA ANJELIA | 27-Dec-23 |  | -9 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181583 | ADIDAS | GK | 290059 | SUMIATI | 58 | 58 | 0 |  | 181587 | ADIDAS | GK | 292100 | TRI LESTARI | 0.348 | 0.3497 | 0.49 | [7 empty] | 181587 | ADIDAS | GK | 290060 | TRI LESTARI | 4.61 | 16 February
181604 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181595 | ADIDAS | GM1 | 267379 | PUTRI EGA ANJELIA | 27-Dec-23 |  | -9 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181587 | ADIDAS | GK | 290059 | SUMIATI | 58 | 58 | 0 |  | 181587 | ADIDAS | GK | 290060 | TRI LESTARI | 0.348 | 0.3497 | 0.49 | [7 empty] | 181586 | ADIDAS | GK | 290059 | TRI LESTARI | 5.18 | 16 February
181605 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181595 | ADIDAS | GM1 | 267376 | PUTRI EGA ANJELIA | 27-Dec-23 |  | -9 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181587 | ADIDAS | GK | 292100 | SUMIATI | 58 | 58 | 0 |  | 181587 | ADIDAS | GK | 290059 | TRI LESTARI | 0.348 | 0.3499 | 0.55 | [7 empty] | 181587 | ADIDAS | GK | 292100 | TRI LESTARI | 6.01 | 16 February
181606 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181595 | ADIDAS | GM1 | 282190 | PUTRI EGA ANJELIA | 27-Dec-23 |  | -9 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181587 | ADIDAS | GK | 290060 | SUMIATI | 58 | 58 | 0 |  | 181583 | ADIDAS | GK | 290059 | TRI LESTARI | 0.335 | 0.3409 | 1.76 | [7 empty] | 181629 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 8.84 | 16 February
181607 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181075 | NISHIMATSUYA, | CVA | 293838 |  | 28-Dec-23 |  | -8 | OK | 181586 | ADIDAS | GK | 290059 | SUMIATI | 58 | 58 | 0 |  | 181629 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 0.201 | 0.2064 | 2.69 | [7 empty] | 181584 | ADIDAS | GK | 290059 | TRI LESTARI | 12.08 | 16 February
181621 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181075 | NISHIMATSUYA, | CVA | 293837 |  | 28-Dec-23 |  | -8 | OK | 181584 | ADIDAS | GK | 290059 | SUMIATI | 58 | 58 | 0 |  | 181586 | ADIDAS | GK | 290059 | TRI LESTARI | 0.33 | 0.3401 | 3.06
181622 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181621 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 29-Dec-23 |  | -7 | KAIN BLM DTG | 181629 | ADIDAS | GM2 | 294353 | SUMIATI | 58
181606 | ADIDAS | GM2 | 292585 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181621 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 29-Dec-23 |  | -7 | KAIN BLM DTG | 181634 | ADIDAS | GM2 | 292107 | SUMIATI | 58
181602 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181599 | ADIDAS | GM1 | 292733 | PUTRI EGA ANJELIA | 29-Dec-23 |  | -7 | KAIN BELUM DATANG, ESTIMASI 08 JANUARI 2024 | 181634 | ADIDAS | GM2 | 293262 | SUMIATI | 58
181603 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181622 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 01-Jan-24 |  | -4 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181592 | ADIDAS | GM1 | 295030 | SUMIATI | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
181604 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181622 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 01-Jan-24 |  | -4 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181592 | ADIDAS | GM1 | 295031 | SUMIATI | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
181605 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181609 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 03-Jan-24 |  | -2 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181593 | ADIDAS | GM1 | 294351 | SUMIATI | 58
181606 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181612 | ADIDAS | GM2 | 292590 | RESTY HERMA ROSTANIKA | 05-Jan-24 |  | 0 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181593 | ADIDAS | GM1 | 294352 | SUMIATI | 58
181621 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181612 | ADIDAS | GM2 | 292587 | RESTY HERMA ROSTANIKA | 05-Jan-24 |  | 0 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181594 | ADIDAS | GM1 | 295032 | SUMIATI | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
181622 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181612 | ADIDAS | GM2 | 292589 | RESTY HERMA ROSTANIKA | 05-Jan-24 |  | 0 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181594 | ADIDAS | GM1 | 295033 | SUMIATI | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
181602 | ADIDAS | GM2 | 292581 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181588 | ADIDAS | GK | 290059 | TRI LESTARI | 08-Jan-24 |  | 3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181595 | ADIDAS | GM1 | 267375 | SUMIATI | 70
181603 | ADIDAS | GM2 | 292581 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181588 | ADIDAS | GK | 290060 | TRI LESTARI | 08-Jan-24 |  | 3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181595 | ADIDAS | GM1 | 282190 | SUMIATI | 70
181638 | ADIDAS | GM2 | 294571 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181588 | ADIDAS | GK | 292100 | TRI LESTARI | 08-Jan-24 |  | 3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181595 | ADIDAS | GM1 | 267376 | SUMIATI | 70
181593 | ADIDAS | GM1 | 294351 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181605 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 08-Jan-24 |  | 3 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181595 | ADIDAS | GM1 | 267379 | SUMIATI | 70
181638 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181607 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 08-Jan-24 |  | 3 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181596 | ADIDAS | GM1 | 295034 | SUMIATI | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
181638 | ADIDAS | GM2 | 292101 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181605 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 08-Jan-24 |  | 3 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181597 | ADIDAS | GM1 | 292731 | SUMIATI | 58
181592 | ADIDAS | GM1 | 295031 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KONTRAK BLM RELEASE | 181608 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 08-Jan-24 |  | 3 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181598 | ADIDAS | GM1 | 292732 | SUMIATI | 58
181592 | ADIDAS | GM1 | 295030 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KONTRAK BLM RELEASE | 181611 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 08-Jan-24 |  | 3 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181599 | ADIDAS | GM1 | 292733 | SUMIATI | 58
181638 | ADIDAS | GM2 | 294572 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BLM DTG | 181589 | ADIDAS | GK | 290059 | TRI LESTARI | 09-Jan-24 |  | 4 |  | 181600 | ADIDAS | GM1 | 292734 | SUMIATI | 58
181594 | ADIDAS | GM1 | 295032 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 05 JANUARI 2024 | 181589 | ADIDAS | GK | 290061 | TRI LESTARI | 09-Jan-24 |  | 4 |  | 181602 | ADIDAS | GM2 | 292581 | SUMIATI | 58
181608 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181589 | ADIDAS | GK | 292730 | TRI LESTARI | 09-Jan-24 |  | 4 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181602 | ADIDAS | GM2 | 292582 | SUMIATI | 58
181609 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181638 | ADIDAS | GM2 | 294571 | RESTY HERMA ROSTANIKA | 09-Jan-24 |  | 4 | KAIN BLM DTG | 181602 | ADIDAS | GM2 | 292578 | SUMIATI | 58
181610 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181638 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 09-Jan-24 |  | 4 | KAIN BLM DTG | 181603 | ADIDAS | GM2 | 292581 | SUMIATI | 58
181611 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181638 | ADIDAS | GM2 | 292101 | RESTY HERMA ROSTANIKA | 09-Jan-24 |  | 4 | KAIN BLM DTG | 181603 | ADIDAS | GM2 | 292582 | SUMIATI | 58
181628 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181638 | ADIDAS | GM2 | 294572 | RESTY HERMA ROSTANIKA | 09-Jan-24 |  | 4 | KAIN BLM DTG | 181603 | ADIDAS | GM2 | 292578 | SUMIATI | 58
181628 | ADIDAS | GM2 | 292588 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181648 | COCOS-S# | CBA | 268104 |  | 10-Jan-24 |  | 5 | KONTRAK RILIS TGL 3 JAN | 181604 | ADIDAS | GM2 | 292578 | SUMIATI | 58
181612 | ADIDAS | GM2 | 292590 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181648 | COCOS-S# | CBA | 269388 |  | 10-Jan-24 |  | 5 | KONTRAK RILIS TGL 3 JAN | 181604 | ADIDAS | GM2 | 292582 | SUMIATI | 58
181612 | ADIDAS | GM2 | 292587 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181648 | COCOS-S# | CBA | 269390 |  | 10-Jan-24 |  | 5 | KONTRAK RILIS TGL 3 JAN | 181605 | ADIDAS | GM2 | 292578 | SUMIATI | 58
181628 | ADIDAS | GM2 | 292587 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181648 | COCOS-S# | CBA | 269389 |  | 10-Jan-24 |  | 5 | KONTRAK RILIS TGL 3 JAN | 181605 | ADIDAS | GM2 | 292582 | SUMIATI | 58
181612 | ADIDAS | GM2 | 292589 | RESTY HERMA ROSTANIKA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181634 | ADIDAS | GM2 | 292107 | RESTY HERMA ROSTANIKA | 11-Jan-24 |  | 6 | KAIN BELUM DATANG, ESTIMASI 03 JANUARI 2024 | 181606 | ADIDAS | GM2 | 292585 | SUMIATI | 58
181613 | ADIDAS | GM1 | 292593 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181634 | ADIDAS | GM2 | 293262 | RESTY HERMA ROSTANIKA | 11-Jan-24 |  | 6 | KAIN BELUM DATANG, ESTIMASI 03 JANUARI 2024 | 181606 | ADIDAS | GM2 | 292578 | SUMIATI | 58
181625 | ADIDAS | GM1 | 292593 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181602 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 11-Jan-24 |  | 6 | KAIN BLM DTG | 181606 | ADIDAS | GM2 | 292582 | SUMIATI | 58
181595 | ADIDAS | GM1 | 267375 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181603 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 11-Jan-24 |  | 6 | KAIN BLM DTG | 181607 | ADIDAS | GM2 | 292578 | SUMIATI | 58
181624 | ADIDAS | GM1 | 267375 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181604 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 11-Jan-24 |  | 6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181608 | ADIDAS | GM2 | 292586 | SUMIATI | 60
181595 | ADIDAS | GM1 | 267379 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181602 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 11-Jan-24 |  | 6 | KAIN BLM DTG | 181609 | ADIDAS | GM2 | 292586 | SUMIATI | 60
181595 | ADIDAS | GM1 | 267376 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181603 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 11-Jan-24 |  | 6 | KAIN BLM DTG | 181610 | ADIDAS | GM2 | 292586 | SUMIATI | 60
181595 | ADIDAS | GM1 | 282190 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181604 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 11-Jan-24 |  | 6 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181611 | ADIDAS | GM2 | 292586 | SUMIATI | 60
181598 | ADIDAS | GM1 | 292732 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 08 JANUARI 2024 | 181602 | ADIDAS | GM2 | 292581 | RESTY HERMA ROSTANIKA | 11-Jan-24 |  | 6 | KAIN BLM DTG | 181612 | ADIDAS | GM2 | 292589 | SUMIATI | 60
181596 | ADIDAS | GM1 | 295034 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 12 JANUARI 2024 | 181603 | ADIDAS | GM2 | 292581 | RESTY HERMA ROSTANIKA | 11-Jan-24 |  | 6 | KAIN BLM DTG | 181612 | ADIDAS | GM2 | 292587 | SUMIATI | 60
181599 | ADIDAS | GM1 | 292733 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 08 JANUARI 2024 | 181593 | ADIDAS | GM1 | 294351 | PUTRI EGA ANJELIA | 11-Jan-24 |  | 6 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181612 | ADIDAS | GM2 | 292590 | SUMIATI | 60
181600 | ADIDAS | GM1 | 292734 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 08 JANUARI 2024 | 181610 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 11-Jan-24 |  | 6 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181613 | ADIDAS | GM1 | 292593 | SUMIATI | 70
181594 | ADIDAS | GM1 | 295033 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 05 JANUARI 2024 | 181593 | ADIDAS | GM1 | 294352 | PUTRI EGA ANJELIA | 11-Jan-24 |  | 6 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181621 | ADIDAS | GM2 | 292578 | SUMIATI | 58
181597 | ADIDAS | GM1 | 292731 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 08 JANUARI 2024 | 181606 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 12-Jan-24 |  | 7 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181621 | ADIDAS | GM2 | 292582 | SUMIATI | 58
181593 | ADIDAS | GM1 | 294352 | PUTRI EGA ANJELIA | 30-Dec-23 |  | -6 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181606 | ADIDAS | GM2 | 292585 | RESTY HERMA ROSTANIKA | 12-Jan-24 |  | 7 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181622 | ADIDAS | GM2 | 292578 | SUMIATI | 58
181626 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 02-Jan-24 |  | -3 |  | 181606 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 12-Jan-24 |  | 7 | KAIN BELUM DATANG, ESTIMASI 13 JANUARI 2024 | 181622 | ADIDAS | GM2 | 292582 | SUMIATI | 58
181588 | ADIDAS | GK | 290059 | TRI LESTARI | 02-Jan-24 |  | -3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181628 | ADIDAS | GM2 | 292586 | RESTY HERMA ROSTANIKA | 12-Jan-24 |  | 7 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181624 | ADIDAS | GM1 | 267375 | SUMIATI | 70
181585 | ADIDAS | GK | 290062 | TRI LESTARI | 02-Jan-24 |  | -3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181628 | ADIDAS | GM2 | 292588 | RESTY HERMA ROSTANIKA | 12-Jan-24 |  | 7 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181625 | ADIDAS | GM1 | 292593 | SUMIATI | 70
181589 | ADIDAS | GK | 292730 | TRI LESTARI | 02-Jan-24 |  | -3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181628 | ADIDAS | GM2 | 292587 | RESTY HERMA ROSTANIKA | 12-Jan-24 |  | 7 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181628 | ADIDAS | GM2 | 292587 | SUMIATI | 60
181626 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 02-Jan-24 |  | -3 | KAIN BLM DTG | 181626 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 15-Jan-24 |  | 10 |  | 181628 | ADIDAS | GM2 | 292586 | SUMIATI | 60
181591 | ADIDAS | GK | 290061 | TRI LESTARI | 02-Jan-24 |  | -3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181626 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 15-Jan-24 |  | 10 | KAIN BLM DTG | 181628 | ADIDAS | GM2 | 292588 | SUMIATI | 60
181590 | ADIDAS | GK | 290061 | TRI LESTARI | 02-Jan-24 |  | -3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181590 | ADIDAS | GK | 290061 | TRI LESTARI | 15-Jan-24 |  | 10 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181638 | ADIDAS | GM2 | 294571 | SUMIATI | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
181591 | ADIDAS | GK | 292101 | TRI LESTARI | 02-Jan-24 |  | -3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181590 | ADIDAS | GK | 292101 | TRI LESTARI | 15-Jan-24 |  | 10 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181638 | ADIDAS | GM2 | 292101 | SUMIATI | 58
181590 | ADIDAS | GK | 292101 | TRI LESTARI | 02-Jan-24 |  | -3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181626 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 15-Jan-24 |  | 10 | KAIN BLM DTG | 181638 | ADIDAS | GM2 | 290061 | SUMIATI | 58
181626 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 02-Jan-24 |  | -3 | KAIN BLM DTG | 181590 | ADIDAS | GK | 293262 | TRI LESTARI | 15-Jan-24 |  | 10 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181638 | ADIDAS | GM2 | 294572 | SUMIATI | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
181588 | ADIDAS | GK | 290060 | TRI LESTARI | 02-Jan-24 |  | -3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181629 | ADIDAS | GM2 | 294353 | RESTY HERMA ROSTANIKA | 15-Jan-24 |  | 10 | KAIN BELUM DATANG, ESTIMASI 03 JANUARI 2024 | 181626 | ADIDAS | GM2 | 290060 | SUMIATI | 58
181591 | ADIDAS | GK | 293262 | TRI LESTARI | 02-Jan-24 |  | -3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181591 | ADIDAS | GK | 290061 | TRI LESTARI | 16-Jan-24 |  | 11 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181626 | ADIDAS | GM2 | 290059 | SUMIATI | 58
181590 | ADIDAS | GK | 293262 | TRI LESTARI | 02-Jan-24 |  | -3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181591 | ADIDAS | GK | 292101 | TRI LESTARI | 16-Jan-24 |  | 11 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181626 | ADIDAS | GM2 | 290061 | SUMIATI | 58
181588 | ADIDAS | GK | 292100 | TRI LESTARI | 02-Jan-24 |  | -3 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181591 | ADIDAS | GK | 293262 | TRI LESTARI | 16-Jan-24 |  | 11 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181591 | ADIDAS | GK | 293262 | SUMIATI | 58
181647 | COCOS-S# | CBA | 268104 |  | 04-Jan-24 |  | -1 | OK | 181596 | ADIDAS | GM1 | 295034 | PUTRI EGA ANJELIA | 16-Jan-24 |  | 11 | KAIN BELUM DATANG, ESTIMASI 12 JANUARI 2024 | 181591 | ADIDAS | GK | 292101 | SUMIATI | 58
181647 | COCOS-S# | CBA | 269388 |  | 04-Jan-24 |  | -1 | OK | 181597 | ADIDAS | GM1 | 292731 | PUTRI EGA ANJELIA | 16-Jan-24 |  | 11 | KAIN BELUM DATANG, ESTIMASI 08 JANUARI 2024 | 181591 | ADIDAS | GK | 290061 | SUMIATI | 58
181647 | COCOS-S# | CBA | 269390 |  | 04-Jan-24 |  | -1 | OK | 181598 | ADIDAS | GM1 | 292732 | PUTRI EGA ANJELIA | 17-Jan-24 |  | 12 | KAIN BELUM DATANG, ESTIMASI 08 JANUARI 2024 | 181590 | ADIDAS | GK | 293262 | SUMIATI | 58
181647 | COCOS-S# | CBA | 269389 |  | 04-Jan-24 |  | -1 | OK | 181423 | BERGANS, | GM1 | 286304 | PUTRI EGA ANJELIA | 19-Jan-24 |  | 14 |  | 181590 | ADIDAS | GK | 292101 | SUMIATI | 58
181423 | BERGANS, | GM1 | 286304 | PUTRI EGA ANJELIA | 04-Jan-24 |  | -1 |  | 181423 | BERGANS, | GM1 | 286306 | PUTRI EGA ANJELIA | 19-Jan-24 |  | 14 | KAIN BELUM DATANG | 181590 | ADIDAS | GK | 290061 | SUMIATI | 58
181423 | BERGANS, | GM1 | 286306 | PUTRI EGA ANJELIA | 04-Jan-24 |  | -1 | KAIN BELUM DATANG | 181600 | ADIDAS | GM1 | 292734 | PUTRI EGA ANJELIA | 19-Jan-24 |  | 14 | KAIN BELUM DATANG, ESTIMASI 08 JANUARI 2024 | 181589 | ADIDAS | GK | 292730 | SUMIATI | 58
[9 empty] | 181585 | ADIDAS | GK | 290063 | TRI LESTARI | 22-Jan-24 |  | 17 |  | 181589 | ADIDAS | GK | 290061 | SUMIATI | 58
[9 empty] | 181585 | ADIDAS | GK | 290061 | TRI LESTARI | 22-Jan-24 |  | 17 |  | 181589 | ADIDAS | GK | 290059 | SUMIATI | 58
[9 empty] | 181585 | ADIDAS | GK | 290062 | TRI LESTARI | 22-Jan-24 |  | 17 | KAIN BELUM DATANG, ESTIMASI 07 JANUARI 2024 | 181588 | ADIDAS | GK | 290059 | SUMIATI | 58
[9 empty] | 181613 | ADIDAS | GM1 | 292593 | PUTRI EGA ANJELIA | 08-Feb-24 |  | 34 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181588 | ADIDAS | GK | 292100 | SUMIATI | 58
[9 empty] | 181624 | ADIDAS | GM1 | 267375 | PUTRI EGA ANJELIA | 13-Feb-24 |  | 39 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181588 | ADIDAS | GK | 290060 | SUMIATI | 58
[9 empty] | 181625 | ADIDAS | GM1 | 292593 | PUTRI EGA ANJELIA | 19-Feb-24 |  | 45 | KAIN BELUM DATANG, ESTIMASI 16 JANUARI 2024 | 181585 | ADIDAS | GK | 290062 | SUMIATI | 58
[9 empty] | 181647 | COCOS-S# | CBA | 268104 |  | 28-Feb-24 |  | 54 | OK | 181585 | ADIDAS | GK | 290061 | SUMIATI | 58
[9 empty] | 181647 | COCOS-S# | CBA | 269388 |  | 28-Feb-24 |  | 54 | OK | 181585 | ADIDAS | GK | 290063 | SUMIATI | 58
[9 empty] | 181647 | COCOS-S# | CBA | 269390 |  | 28-Feb-24 |  | 54 | OK | 181648 | COCOS-S# | CBA | 268104 | GITA | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[9 empty] | 181647 | COCOS-S# | CBA | 269389 |  | 28-Feb-24 |  | 54 | OK | 181648 | COCOS-S# | CBA | 269388 | GITA | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181648 | COCOS-S# | CBA | 269390 | GITA | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181648 | COCOS-S# | CBA | 269389 | GITA | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181075 | NISHIMATSUYA, | CVA | 293837 | GITA | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181075 | NISHIMATSUYA, | CVA | 293838 | GITA | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181423 | BERGANS, | GM1 | 286306 |  | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181423 | BERGANS, | GM1 | 286304 |  | 50
[18 empty] | 181647 | COCOS-S# | CBA | 268104 |  | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181647 | COCOS-S# | CBA | 269388 |  | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181647 | COCOS-S# | CBA | 269390 |  | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181647 | COCOS-S# | CBA | 269389 |  | 0 |  |  | Plan Lebar Kain Tidak Ditemukan