## REPORT HASIL
Co Date vs Fabric Receipt in Cutting Date | [8 empty] | Start Cutting Date vs PPIC Date | [8 empty] | Lebar Kain Plan vs Lebar Kain Actual | [8 empty] | Consumption Plan vs Consumption Actual | [7 empty] | Garment Short/Over (Pcs) | [6 empty] | Sisa Fabric
WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE
181941 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -1 | PLAN CUTTING MID FEB | 181857 | STYLEM, | GK | 296018 | TRI LESTARI | 29-Jan-24 |  | -1 | KAIN OK, PLAN CUTT TGL 26 JANUARI 2024 | 181857 | STYLEM, | GK | 296016 |  | 135 | 52 | -61.48 | KAIN OK, PLAN CUTT TGL 26 JANUARI 2024 | 181857 | STYLEM, | GK | 296019 | TRI LESTARI | 2.1973 | 1.4324 | -34.81 | 181437 | SKECHERS-S# | CVA | 294605 | NOFITA CICILIA | -17.86 | 02 February | 181857 | STYLEM, | GK | 296017 | TRI LESTARI | 1.42 | 15 March
181942 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -1 | PLAN CUTTING MID FEB | 181713 | ADIDAS | GK | 290059 | TRI LESTARI | 31-Jan-24 |  | 1 |  | 181857 | STYLEM, | GK | 296017 |  | 135 | 53 | -60.74 | KAIN OK, PLAN CUTT TGL 26 JANUARI 2024 | 181857 | STYLEM, | GK | 296017 | TRI LESTARI | 2.2357 | 2.1833 | -2.34 | 181439 | SKECHERS-S# | CVA | 294606 | NOFITA CICILIA | -13.73 | 02 February | 181437 | SKECHERS-S# | CVA | 294605 | NOFITA CICILIA | 2.35 | 02 February
181941 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -1 | PLAN CUTTING MID FEB | 181713 | ADIDAS | GK | 292102 | TRI LESTARI | 31-Jan-24 |  | 1 |  | 181857 | STYLEM, | GK | 296019 |  | 135 | 133.4 | -1.19 | KAIN OK, PLAN CUTT TGL 26 JANUARI 2024 | 181925 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.331 | 0.3256 | -1.63 | 181857 | STYLEM, | GK | 296019 | TRI LESTARI | 0.19 | 15 March | 181439 | SKECHERS-S# | CVA | 294606 | NOFITA CICILIA | 2.46 | 02 February
181942 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -1 | PLAN CUTTING MID FEB | 181713 | ADIDAS | GK | 290060 | TRI LESTARI | 31-Jan-24 |  | 1 |  | 181439 | SKECHERS-S# | CVA | 294606 | GITA | 58 | 58.8 | 1.29 |  | 181925 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 0.331 | 0.3277 | -1 | [7 empty] | 181857 | STYLEM, | GK | 296019 | TRI LESTARI | 3.66 | 15 March
181941 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -1 | PLAN CUTTING MID FEB | 181758 | KAZEN-S# | CNJ2 | 247752 |  | 02-Feb-24 |  | 3 | KAIN DATANG PARTIAL, PLAN CUTT TGL 15 FEB 2024 | 181442 | SKECHERS-S# | CVA | 294613 | GITA | 62 | 63 | 1.61 |  | 181925 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | 0.331 | 0.3282 | -0.85 | [7 empty] | 181857 | STYLEM, | GK | 296016 | TRI LESTARI | 4.76 | 15 March
181942 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -1 | PLAN CUTTING MID FEB | 181858 | STYLEM, | GK | 296019 | TRI LESTARI | 05-Feb-24 |  | 6 | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181443 | SKECHERS-S# | CVA | 294613 | GITA | 62 | 63 | 1.61 |  | 181442 | SKECHERS-S# | CVA | 294613 | NOFITA CICILIA | 0.634 | 0.6331 | -0.14 | [7 empty] | 181450 | SKECHERS-S# | CVA | 294613 | NOFITA CICILIA | 8.66 | 07 February
181941 | ADIDAS | GM1 | 290064 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -1 | PLAN CUTTING MID FEB | 181858 | STYLEM, | GK | 296017 | TRI LESTARI | 05-Feb-24 |  | 6 | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181450 | SKECHERS-S# | CVA | 294613 | GITA | 62 | 63 | 1.61 |  | 181437 | SKECHERS-S# | CVA | 294605 | NOFITA CICILIA | 0.575 | 0.5745 | -0.09
181942 | ADIDAS | GM1 | 292735 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -1 | PLAN CUTTING MID FEB | 181858 | STYLEM, | GK | 296016 | TRI LESTARI | 05-Feb-24 |  | 6 | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181437 | SKECHERS-S# | CVA | 294605 | GITA | 58 | 60 | 3.45 |  | 181450 | SKECHERS-S# | CVA | 294613 | NOFITA CICILIA | 0.721 | 0.7205 | -0.07
181758 | KAZEN-S# | CNJ2 | 247752 |  | 30-Jan-24 |  | 0 | KAIN DATANG PARTIAL, PLAN CUTT TGL 15 FEB 2024 | 181858 | STYLEM, | GK | 296018 | TRI LESTARI | 05-Feb-24 |  | 6 | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181928 | ADIDAS | GM2 | 290059 | SUMIATI | 58 |  |  |  | 181937 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.462 | 0.4617 | -0.06
181753 | KAZEN-S# | CNJ2 | 247750 |  | 30-Jan-24 |  | 0 | KAIN OK, PLAN CUTT TGL 17 FEB 2024 | 181859 | STYLEM, | GK | 296019 | TRI LESTARI | 06-Feb-24 |  | 7 | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181930 | ADIDAS | GM2 | 293955 | SUMIATI | 58 |  |  |  | 181937 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 0.462 | 0.4617 | -0.06
[9 empty] | 181859 | STYLEM, | GK | 296017 | TRI LESTARI | 06-Feb-24 |  | 7 | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181930 | ADIDAS | GM2 | 292101 | SUMIATI | 58 |  |  |  | 181937 | ADIDAS | GM2 | 290063 | RESTY HERMA ROSTANIKA | 0.462 | 0.4617 | -0.06
[9 empty] | 181859 | STYLEM, | GK | 296016 | TRI LESTARI | 06-Feb-24 |  | 7 | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181930 | ADIDAS | GM2 | 292107 | SUMIATI | 58 |  |  |  | 181926 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | 0.411 | 0.4108 | -0.05
[9 empty] | 181859 | STYLEM, | GK | 296018 | TRI LESTARI | 06-Feb-24 |  | 7 | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181933 | ADIDAS | GM2 | 290060 | SUMIATI | 58 |  |  |  | 181926 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.411 | 0.4108 | -0.05
[9 empty] | 181753 | KAZEN-S# | CNJ2 | 247750 |  | 10-Feb-24 |  | 11 | KAIN OK, PLAN CUTT TGL 17 FEB 2024 | 181933 | ADIDAS | GM2 | 290061 | SUMIATI | 58 |  |  |  | 181926 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 0.411 | 0.4108 | -0.05
[9 empty] | 181714 | ADIDAS | GK | 290059 | TRI LESTARI | 12-Feb-24 |  | 13 |  | 181857 | STYLEM, | GK | 296018 |  | 135 |  |  | KAIN OK, PLAN CUTT TGL 26 JANUARI 2024 | 181439 | SKECHERS-S# | CVA | 294606 | NOFITA CICILIA | 0.584 | 0.5839 | -0.02
[9 empty] | 181714 | ADIDAS | GK | 292102 | TRI LESTARI | 12-Feb-24 |  | 13 |  | 181858 | STYLEM, | GK | 296016 |  | 135 |  |  | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181443 | SKECHERS-S# | CVA | 294613 | NOFITA CICILIA | 0.633 | 0.6331 | 0.02
[9 empty] | 181714 | ADIDAS | GK | 290060 | TRI LESTARI | 12-Feb-24 |  | 13 |  | 181858 | STYLEM, | GK | 296017 |  | 135 |  |  | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181936 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 0.395 | 0.3952 | 0.05
[9 empty] | 181933 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 21-Feb-24 |  | 22 |  | 181858 | STYLEM, | GK | 296018 |  | 135 |  |  | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181936 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.395 | 0.3956 | 0.15
[9 empty] | 181933 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 21-Feb-24 |  | 22 |  | 181858 | STYLEM, | GK | 296019 |  | 135 |  |  | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181933 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.376 | 0.377 | 0.27
[9 empty] | 181942 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 25-Feb-24 |  | 26 | PLAN CUTTING MID FEB | 181859 | STYLEM, | GK | 296016 |  | 135 |  |  | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181936 | ADIDAS | GM2 | 290063 | RESTY HERMA ROSTANIKA | 0.395 | 0.3962 | 0.3
[9 empty] | 181942 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 25-Feb-24 |  | 26 | PLAN CUTTING MID FEB | 181859 | STYLEM, | GK | 296017 |  | 135 |  |  | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181857 | STYLEM, | GK | 296016 | TRI LESTARI | 2.2357 | 2.2729 | 1.66
[9 empty] | 181942 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 25-Feb-24 |  | 26 | PLAN CUTTING MID FEB | 181859 | STYLEM, | GK | 296018 |  | 135 |  |  | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181927 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.332 | 0.3383 | 1.9
[9 empty] | 181942 | ADIDAS | GM1 | 292735 | PUTRI EGA ANJELIA | 25-Feb-24 |  | 26 | PLAN CUTTING MID FEB | 181859 | STYLEM, | GK | 296019 |  | 135 |  |  | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024
[9 empty] | 181929 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 27-Feb-24 |  | 28 |  | 181713 | ADIDAS | GK | 292102 | SUMIATI | 58
[9 empty] | 181929 | ADIDAS | GM2 | 292730 | RESTY HERMA ROSTANIKA | 27-Feb-24 |  | 28 |  | 181713 | ADIDAS | GK | 290059 | SUMIATI | 58
[9 empty] | 181929 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 27-Feb-24 |  | 28 |  | 181713 | ADIDAS | GK | 290060 | SUMIATI | 58
[9 empty] | 181930 | ADIDAS | GM2 | 292101 | RESTY HERMA ROSTANIKA | 29-Feb-24 |  | 30 |  | 181714 | ADIDAS | GK | 292102 | SUMIATI | 58
[9 empty] | 181930 | ADIDAS | GM2 | 292107 | RESTY HERMA ROSTANIKA | 29-Feb-24 |  | 30 |  | 181714 | ADIDAS | GK | 290059 | SUMIATI | 58
[9 empty] | 181930 | ADIDAS | GM2 | 293955 | RESTY HERMA ROSTANIKA | 29-Feb-24 |  | 30 |  | 181714 | ADIDAS | GK | 290060 | SUMIATI | 58
[9 empty] | 181928 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 01-Mar-24 |  | 31 |  | 181929 | ADIDAS | GM2 | 292730 | SUMIATI | 58
[9 empty] | 181941 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 11-Mar-24 |  | 41 | PLAN CUTTING MID FEB | 181929 | ADIDAS | GM2 | 290061 | SUMIATI | 58
[9 empty] | 181941 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 11-Mar-24 |  | 41 | PLAN CUTTING MID FEB | 181929 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[9 empty] | 181941 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 11-Mar-24 |  | 41 | PLAN CUTTING MID FEB | 181941 | ADIDAS | GM1 | 290064 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[9 empty] | 181941 | ADIDAS | GM1 | 290064 | PUTRI EGA ANJELIA | 11-Mar-24 |  | 41 | PLAN CUTTING MID FEB | 181941 | ADIDAS | GM1 | 290059 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181941 | ADIDAS | GM1 | 290060 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181941 | ADIDAS | GM1 | 290061 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181942 | ADIDAS | GM1 | 292735 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181942 | ADIDAS | GM1 | 290059 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181942 | ADIDAS | GM1 | 290060 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181942 | ADIDAS | GM1 | 290061 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181753 | KAZEN-S# | CNJ2 | 247750 |  | 59 |  |  | KAIN OK, PLAN CUTT TGL 17 FEB 2024
[18 empty] | 181758 | KAZEN-S# | CNJ2 | 247752 |  | 59 |  |  | KAIN DATANG PARTIAL, PLAN CUTT TGL 15 FEB 2024