## REPORT HASIL
Co Date vs Fabric Receipt in Cutting Date | [8 empty] | Start Cutting Date vs PPIC Date | [8 empty] | Lebar Kain Plan vs Lebar Kain Actual | [8 empty] | Consumption Plan vs Consumption Actual | [7 empty] | Garment Short/Over (Pcs) | [6 empty] | Sisa Fabric
WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE
181941 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -2 | PLAN CUTTING MID FEB | 181758 | KAZEN-S# | CNJ2 | 247752 |  | 02-Feb-24 |  | 2 | KAIN DATANG PARTIAL, PLAN CUTT TGL 15 FEB 2024 | 181857 | STYLEM, | GK | 296016 |  | 54 | 52 | -3.7 | KAIN OK, PLAN CUTT TGL 26 JANUARI 2024 | 181857 | STYLEM, | GK | 296017 | TRI LESTARI | 2.2357 | 2.1833 | -2.34 | 181857 | STYLEM, | GK | 296019 | TRI LESTARI | 0.19 | 15 March | 181713 | ADIDAS | GK | 290059 | TRI LESTARI | 0.02 | 01 March
181942 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -2 | PLAN CUTTING MID FEB | 181858 | STYLEM, | GK | 296019 | TRI LESTARI | 05-Feb-24 |  | 5 | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181857 | STYLEM, | GK | 296018 |  | 54 | 52.4 | -2.96 | KAIN OK, PLAN CUTT TGL 26 JANUARI 2024 | 181857 | STYLEM, | GK | 296019 | TRI LESTARI | 2.1973 | 2.1486 | -2.22 | 181451 | SKECHERS-S# | CVA | 294613 | NOFITA CICILIA | 3.84 | 07 February | 181713 | ADIDAS | GK | 290060 | TRI LESTARI | 0.04 | 01 March
181941 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -2 | PLAN CUTTING MID FEB | 181858 | STYLEM, | GK | 296017 | TRI LESTARI | 05-Feb-24 |  | 5 | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181857 | STYLEM, | GK | 296017 |  | 54 | 53 | -1.85 | KAIN OK, PLAN CUTT TGL 26 JANUARI 2024 | 181713 | ADIDAS | GK | 292102 | TRI LESTARI | 0.332 | 0.3285 | -1.05 | [7 empty] | 181713 | ADIDAS | GK | 292102 | TRI LESTARI | 0.16 | 01 March
181942 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -2 | PLAN CUTTING MID FEB | 181858 | STYLEM, | GK | 296016 | TRI LESTARI | 05-Feb-24 |  | 5 | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181713 | ADIDAS | GK | 292102 | SUMIATI | 58 | 58.4 | 0.69 |  | 181713 | ADIDAS | GK | 290059 | TRI LESTARI | 0.332 | 0.3285 | -1.05 | [7 empty] | 181857 | STYLEM, | GK | 296017 | TRI LESTARI | 1.42 | 15 March
181941 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -2 | PLAN CUTTING MID FEB | 181858 | STYLEM, | GK | 296018 | TRI LESTARI | 05-Feb-24 |  | 5 | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181713 | ADIDAS | GK | 290059 | SUMIATI | 58 | 58.4 | 0.69 |  | 181713 | ADIDAS | GK | 290060 | TRI LESTARI | 0.332 | 0.3285 | -1.05 | [7 empty] | 181857 | STYLEM, | GK | 296018 | TRI LESTARI | 2.42 | 15 March
181942 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -2 | PLAN CUTTING MID FEB | 181859 | STYLEM, | GK | 296019 | TRI LESTARI | 06-Feb-24 |  | 6 | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181713 | ADIDAS | GK | 290060 | SUMIATI | 58 | 58.4 | 0.69 |  | 181925 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 0.331 | 0.3277 | -1 | [7 empty] | 181857 | STYLEM, | GK | 296019 | TRI LESTARI | 3.66 | 15 March
181941 | ADIDAS | GM1 | 290064 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -2 | PLAN CUTTING MID FEB | 181859 | STYLEM, | GK | 296017 | TRI LESTARI | 06-Feb-24 |  | 6 | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181442 | SKECHERS-S# | CVA | 294613 | GITA | 62 | 63 | 1.61 |  | 181925 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | 0.331 | 0.3278 | -0.97 | [7 empty] | 181857 | STYLEM, | GK | 296016 | TRI LESTARI | 4.76 | 15 March
181942 | ADIDAS | GM1 | 292735 | PUTRI EGA ANJELIA | 29-Jan-24 |  | -2 | PLAN CUTTING MID FEB | 181859 | STYLEM, | GK | 296016 | TRI LESTARI | 06-Feb-24 |  | 6 | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181443 | SKECHERS-S# | CVA | 294613 | GITA | 62 | 63 | 1.61 |  | 181442 | SKECHERS-S# | CVA | 294613 | NOFITA CICILIA | 0.634 | 0.6331 | -0.14 | [7 empty] | 181450 | SKECHERS-S# | CVA | 294613 | NOFITA CICILIA | 8.66 | 07 February
181758 | KAZEN-S# | CNJ2 | 247752 |  | 30-Jan-24 |  | -1 | KAIN DATANG PARTIAL, PLAN CUTT TGL 15 FEB 2024 | 181859 | STYLEM, | GK | 296018 | TRI LESTARI | 06-Feb-24 |  | 6 | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181450 | SKECHERS-S# | CVA | 294613 | GITA | 62 | 63 | 1.61 |  | 181857 | STYLEM, | GK | 296018 | TRI LESTARI | 2.2357 | 2.2329 | -0.13 | [7 empty] | 181451 | SKECHERS-S# | CVA | 294613 | NOFITA CICILIA | 9.13 | 07 February
181753 | KAZEN-S# | CNJ2 | 247750 |  | 30-Jan-24 |  | -1 | KAIN OK, PLAN CUTT TGL 17 FEB 2024 | 181851 | TOYOTA | CNJ2 | 292189 |  | 09-Feb-24 |  | 9 | KAIN OK,PLAN CUTT 9 FEB 2024 | 181451 | SKECHERS-S# | CVA | 294613 | GITA | 62 | 63 | 1.61 |  | 181450 | SKECHERS-S# | CVA | 294613 | NOFITA CICILIA | 0.721 | 0.7205 | -0.07
181851 | TOYOTA | CNJ2 | 292189 |  | 31-Jan-24 |  | 0 | KAIN OK,PLAN CUTT 9 FEB 2024 | 181753 | KAZEN-S# | CNJ2 | 247750 |  | 10-Feb-24 |  | 10 | KAIN OK, PLAN CUTT TGL 17 FEB 2024 | 181858 | STYLEM, | GK | 296016 |  | 54 |  |  | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181451 | SKECHERS-S# | CVA | 294613 | NOFITA CICILIA | 0.721 | 0.7205 | -0.07
[9 empty] | 181714 | ADIDAS | GK | 290059 | TRI LESTARI | 12-Feb-24 |  | 12 |  | 181858 | STYLEM, | GK | 296017 |  | 54 |  |  | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181937 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.462 | 0.4617 | -0.06
[9 empty] | 181714 | ADIDAS | GK | 292102 | TRI LESTARI | 12-Feb-24 |  | 12 |  | 181858 | STYLEM, | GK | 296018 |  | 54 |  |  | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181937 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 0.462 | 0.4617 | -0.06
[9 empty] | 181714 | ADIDAS | GK | 290060 | TRI LESTARI | 12-Feb-24 |  | 12 |  | 181858 | STYLEM, | GK | 296019 |  | 54 |  |  | KAIN OK, PLAN CUTT TGL 05 FEBRUARI 2024 | 181937 | ADIDAS | GM2 | 290063 | RESTY HERMA ROSTANIKA | 0.462 | 0.4617 | -0.06
[9 empty] | 181942 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 25-Feb-24 |  | 25 | PLAN CUTTING MID FEB | 181859 | STYLEM, | GK | 296016 |  | 54 |  |  | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181926 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | 0.411 | 0.4108 | -0.05
[9 empty] | 181942 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 25-Feb-24 |  | 25 | PLAN CUTTING MID FEB | 181859 | STYLEM, | GK | 296017 |  | 54 |  |  | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181926 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.411 | 0.4108 | -0.05
[9 empty] | 181942 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 25-Feb-24 |  | 25 | PLAN CUTTING MID FEB | 181859 | STYLEM, | GK | 296018 |  | 54 |  |  | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181926 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 0.411 | 0.4108 | -0.05
[9 empty] | 181942 | ADIDAS | GM1 | 292735 | PUTRI EGA ANJELIA | 25-Feb-24 |  | 25 | PLAN CUTTING MID FEB | 181859 | STYLEM, | GK | 296019 |  | 54 |  |  | KAIN OK,PLAN CUT TGL 06 FEBRUARI 2024 | 181443 | SKECHERS-S# | CVA | 294613 | NOFITA CICILIA | 0.633 | 0.6331 | 0.02
[9 empty] | 181929 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 27-Feb-24 |  | 27 |  | 181714 | ADIDAS | GK | 292102 | SUMIATI | 58 |  |  |  | 181936 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.395 | 0.3957 | 0.18
[9 empty] | 181929 | ADIDAS | GM2 | 292730 | RESTY HERMA ROSTANIKA | 27-Feb-24 |  | 27 |  | 181714 | ADIDAS | GK | 290059 | SUMIATI | 58 |  |  |  | 181857 | STYLEM, | GK | 296016 | TRI LESTARI | 2.2357 | 2.2729 | 1.66
[9 empty] | 181929 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 27-Feb-24 |  | 27 |  | 181714 | ADIDAS | GK | 290060 | SUMIATI | 58 |  |  |  | 181925 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.331 | 0.3371 | 1.84
[9 empty] | 181941 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 11-Mar-24 |  | 40 | PLAN CUTTING MID FEB | 181929 | ADIDAS | GM2 | 292730 | SUMIATI | 58 |  |  |  | 181936 | ADIDAS | GM2 | 290063 | RESTY HERMA ROSTANIKA | 0.395 | 0.4025 | 1.9
[9 empty] | 181941 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 11-Mar-24 |  | 40 | PLAN CUTTING MID FEB | 181929 | ADIDAS | GM2 | 290061 | SUMIATI | 58 |  |  |  | 181936 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 0.395 | 0.4027 | 1.95
[9 empty] | 181941 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 11-Mar-24 |  | 40 | PLAN CUTTING MID FEB | 181929 | ADIDAS | GM2 | 290059 | SUMIATI | 58 |  |  |  | 181927 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.332 | 0.3386 | 1.99
[9 empty] | 181941 | ADIDAS | GM1 | 290064 | PUTRI EGA ANJELIA | 11-Mar-24 |  | 40 | PLAN CUTTING MID FEB | 181941 | ADIDAS | GM1 | 290064 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181941 | ADIDAS | GM1 | 290059 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181941 | ADIDAS | GM1 | 290060 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181941 | ADIDAS | GM1 | 290061 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181942 | ADIDAS | GM1 | 292735 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181942 | ADIDAS | GM1 | 290059 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181942 | ADIDAS | GM1 | 290060 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181942 | ADIDAS | GM1 | 290061 | SUMIATI | 58 |  |  | PLAN CUTTING MID FEB
[18 empty] | 181753 | KAZEN-S# | CNJ2 | 247750 |  | 59 |  |  | KAIN OK, PLAN CUTT TGL 17 FEB 2024
[18 empty] | 181758 | KAZEN-S# | CNJ2 | 247752 |  | 59 |  |  | KAIN DATANG PARTIAL, PLAN CUTT TGL 15 FEB 2024
[18 empty] | 181851 | TOYOTA | CNJ2 | 292189 | MARTINI | 0 |  |  | KAIN OK,PLAN CUTT 9 FEB 2024