## REPORT HASIL
Co Date vs Fabric Receipt in Cutting Date | [8 empty] | Start Cutting Date vs PPIC Date | [8 empty] | Lebar Kain Plan vs Lebar Kain Actual | [8 empty] | Consumption Plan vs Consumption Actual | [7 empty] | Garment Short/Over (Pcs) | [6 empty] | Sisa Fabric
WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE
181993 | ADIDAS | GM2 | 267376 | RESTY HERMA ROSTANIKA | 09-Feb-24 |  | -7 | KAIN BLM DTG | 181865 | NISHIMATSUYA, | CVA | 287317 | NOFITA CICILIA | 03-Feb-24 |  | -13 | plan cutting di tanggal 21/02PLAN DATANG KAIN 13/02 PARTIAL | 181865 | NISHIMATSUYA, | CVA | 287318 | GITA | 42 | 42.5 | 1.16 |  | 181865 | NISHIMATSUYA, | CVA | 287318 | NOFITA CICILIA | 0.071 | 0.0692 | -2.54 | 182002 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | -27.39 | 01 March | 181865 | NISHIMATSUYA, | CVA | 287319 | NOFITA CICILIA | 1.21 | 22 April
181994 | ADIDAS | GM2 | 267376 | RESTY HERMA ROSTANIKA | 09-Feb-24 |  | -7 | KAIN BLM DTG | 181865 | NISHIMATSUYA, | CVA | 287403 | NOFITA CICILIA | 03-Feb-24 |  | -13 | plan cutting di tanggal 21/02 | 182004 | ADIDAS | GM1 | 290059 | SUMIATI | 58 | 58.7 | 1.25 |  | 182069 | AITOZ, | CLN | 246810 | MUGIARTI | 1.2162 | 1.205 | -0.92 | 181441 | SKECHERS-S# | CVA | 294609 | NOFITA CICILIA | -15.44 | 19 February | 181865 | NISHIMATSUYA, | CVA | 287318 | NOFITA CICILIA | 3.48 | 22 April
181865 | NISHIMATSUYA, | CVA | 287317 | NOFITA CICILIA | 12-Feb-24 |  | -4 | plan cutting di tanggal 21/02PLAN DATANG KAIN 13/02 PARTIAL | 182004 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 04-Mar-24 |  | 17 |  | 182004 | ADIDAS | GM1 | 290064 | SUMIATI | 58 | 59 | 1.72 |  | 182004 | ADIDAS | GM1 | 290064 | PUTRI EGA ANJELIA | 0.338 | 0.3352 | -0.83 | 181865 | NISHIMATSUYA, | CVA | 287318 | NOFITA CICILIA | -6.51 | 22 April | 181999 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | 4.72 | 15 March
181865 | NISHIMATSUYA, | CVA | 287403 | NOFITA CICILIA | 12-Feb-24 |  | -4 | plan cutting di tanggal 21/02 | 181999 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 12-Mar-24 |  | 25 |  | 182069 | AITOZ, | CLN | 246810 |  | 57 | 58.2 | 2.04 |  | 181999 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | 0.34 | 0.3378 | -0.65 | 181865 | NISHIMATSUYA, | CVA | 287319 | NOFITA CICILIA | -2.27 | 22 April | 182069 | AITOZ, | CLN | 246810 | MUGIARTI | 5.43 | 15 March
182000 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 15-Feb-24 |  | -1 |  | 181999 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 12-Mar-24 |  | 25 |  | 181865 | NISHIMATSUYA, | CVA | 287319 | GITA | 42 | 43 | 2.38 |  | 182002 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.339 | 0.3375 | -0.44 | 181963 | ADIDAS | GM2 | 292584 | RESTY HERMA ROSTANIKA | -0.59 | 15 March | 182004 | ADIDAS | GM1 | 290064 | PUTRI EGA ANJELIA | 5.48 | 15 March
[9 empty] | 181999 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 12-Mar-24 |  | 25 |  | 182004 | ADIDAS | GM1 | 290060 | SUMIATI | 58 |  |  |  | 182004 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 0.338 | 0.337 | -0.3 | 182004 | ADIDAS | GM1 | 290064 | PUTRI EGA ANJELIA | 0.01 | 15 March | 181440 | SKECHERS-S# | CVA | 294609 | NOFITA CICILIA | 6.14 | 19 February
[9 empty] | 182000 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 14-Mar-24 |  | 27 |  | 181962 | ADIDAS | GM2 | 292578 | SUMIATI | 58 |  |  |  | 182002 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 0.339 | 0.3408 | 0.53 | [7 empty] | 181441 | SKECHERS-S# | CVA | 294609 | NOFITA CICILIA | 10.3 | 19 February
[9 empty] | 181993 | ADIDAS | GM2 | 267375 | RESTY HERMA ROSTANIKA | 20-Mar-24 |  | 33 |  | 181962 | ADIDAS | GM2 | 292582 | SUMIATI | 58 |  |  |  | 181440 | SKECHERS-S# | CVA | 294609 | NOFITA CICILIA | 0.958 | 0.9646 | 0.69 | [7 empty] | 182004 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 10.69 | 15 March
[9 empty] | 181993 | ADIDAS | GM2 | 267379 | RESTY HERMA ROSTANIKA | 20-Mar-24 |  | 33 |  | 181963 | ADIDAS | GM2 | 292583 | SUMIATI | 58 |  |  |  | 181441 | SKECHERS-S# | CVA | 294609 | NOFITA CICILIA | 0.957 | 0.9646 | 0.79 | [7 empty] | 182002 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 13.27 | 01 March
[9 empty] | 181993 | ADIDAS | GM2 | 267376 | RESTY HERMA ROSTANIKA | 20-Mar-24 |  | 33 | KAIN BLM DTG | 181963 | ADIDAS | GM2 | 292584 | SUMIATI | 58 |  |  |  | 181865 | NISHIMATSUYA, | CVA | 287319 | NOFITA CICILIA | 0.07 | 0.0706 | 0.86 | [7 empty] | 182002 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 21.56 | 01 March
[9 empty] | 181962 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 21-Mar-24 |  | 34 |  | 181963 | ADIDAS | GM2 | 292582 | SUMIATI | 58
[9 empty] | 181962 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 21-Mar-24 |  | 34 |  | 181964 | ADIDAS | GM2 | 292583 | SUMIATI | 58
[9 empty] | 181994 | ADIDAS | GM2 | 267375 | RESTY HERMA ROSTANIKA | 21-Mar-24 |  | 34 |  | 181964 | ADIDAS | GM2 | 292584 | SUMIATI | 58
[9 empty] | 181994 | ADIDAS | GM2 | 267379 | RESTY HERMA ROSTANIKA | 21-Mar-24 |  | 34 |  | 181964 | ADIDAS | GM2 | 292582 | SUMIATI | 58
[9 empty] | 181994 | ADIDAS | GM2 | 267376 | RESTY HERMA ROSTANIKA | 21-Mar-24 |  | 34 | KAIN BLM DTG | 181965 | ADIDAS | GM2 | 292578 | SUMIATI | 58
[9 empty] | 181963 | ADIDAS | GM2 | 292584 | RESTY HERMA ROSTANIKA | 22-Mar-24 |  | 35 |  | 181977 | ADIDAS | GM2 | 292578 | SUMIATI | 58
[9 empty] | 181963 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 22-Mar-24 |  | 35 |  | 181977 | ADIDAS | GM2 | 292582 | SUMIATI | 58
[9 empty] | 181963 | ADIDAS | GM2 | 292583 | RESTY HERMA ROSTANIKA | 22-Mar-24 |  | 35 |  | 181966 | ADIDAS | GM2 | 292573 | SUMIATI | 58
[9 empty] | 181964 | ADIDAS | GM2 | 292584 | RESTY HERMA ROSTANIKA | 25-Mar-24 |  | 38 |  | 181966 | ADIDAS | GM2 | 292578 | SUMIATI | 58
[9 empty] | 181964 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 25-Mar-24 |  | 38 |  | 181967 | ADIDAS | GM2 | 292573 | SUMIATI | 58
[9 empty] | 181964 | ADIDAS | GM2 | 292583 | RESTY HERMA ROSTANIKA | 25-Mar-24 |  | 38 |  | 181967 | ADIDAS | GM2 | 292578 | SUMIATI | 58
[9 empty] | 181995 | ADIDAS | GM2 | 267379 | RESTY HERMA ROSTANIKA | 25-Mar-24 |  | 38 |  | 181993 | ADIDAS | GM2 | 267375 | SUMIATI | 70
[9 empty] | 181995 | ADIDAS | GM2 | 274144 | RESTY HERMA ROSTANIKA | 25-Mar-24 |  | 38 |  | 181993 | ADIDAS | GM2 | 267376 | SUMIATI | 70
[9 empty] | 181995 | ADIDAS | GM2 | 282193 | RESTY HERMA ROSTANIKA | 25-Mar-24 |  | 38 |  | 181993 | ADIDAS | GM2 | 267379 | SUMIATI | 70
[9 empty] | 181965 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 26-Mar-24 |  | 39 |  | 181994 | ADIDAS | GM2 | 267375 | SUMIATI | 70
[9 empty] | 181966 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 27-Mar-24 |  | 40 |  | 181994 | ADIDAS | GM2 | 267376 | SUMIATI | 70
[9 empty] | 181967 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 27-Mar-24 |  | 40 |  | 181994 | ADIDAS | GM2 | 267379 | SUMIATI | 70
[9 empty] | 181966 | ADIDAS | GM2 | 292573 | RESTY HERMA ROSTANIKA | 27-Mar-24 |  | 40 |  | 181995 | ADIDAS | GM2 | 274144 | SUMIATI | 70
[9 empty] | 181967 | ADIDAS | GM2 | 292573 | RESTY HERMA ROSTANIKA | 27-Mar-24 |  | 40 |  | 181995 | ADIDAS | GM2 | 282193 | SUMIATI | 70
[9 empty] | 181996 | ADIDAS | GM2 | 267379 | RESTY HERMA ROSTANIKA | 27-Mar-24 |  | 40 |  | 181995 | ADIDAS | GM2 | 267379 | SUMIATI | 70
[9 empty] | 181996 | ADIDAS | GM2 | 274144 | RESTY HERMA ROSTANIKA | 27-Mar-24 |  | 40 |  | 181996 | ADIDAS | GM2 | 274144 | SUMIATI | 70
[9 empty] | 181996 | ADIDAS | GM2 | 282193 | RESTY HERMA ROSTANIKA | 27-Mar-24 |  | 40 |  | 181996 | ADIDAS | GM2 | 282193 | SUMIATI | 70
[9 empty] | 181977 | ADIDAS | GM2 | 292578 | RESTY HERMA ROSTANIKA | 29-Mar-24 |  | 42 |  | 181996 | ADIDAS | GM2 | 267379 | SUMIATI | 70
[9 empty] | 181977 | ADIDAS | GM2 | 292582 | RESTY HERMA ROSTANIKA | 29-Mar-24 |  | 42 |  | 181865 | NISHIMATSUYA, | CVA | 287403 | GITA | 42
[18 empty] | 181865 | NISHIMATSUYA, | CVA | 287317 | GITA | 42
[18 empty] | 181999 | ADIDAS | GM2 | 290060 | SUMIATI | 58
[18 empty] | 181999 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[18 empty] | 181999 | ADIDAS | GM2 | 290061 | SUMIATI | 58
[18 empty] | 182000 | ADIDAS | GM2 | 290059 | SUMIATI | 58