## REPORT HASIL
Co Date vs Fabric Receipt in Cutting Date | [8 empty] | Start Cutting Date vs PPIC Date | [8 empty] | Lebar Kain Plan vs Lebar Kain Actual | [8 empty] | Consumption Plan vs Consumption Actual | [7 empty] | Garment Short/Over (Pcs) | [6 empty] | Sisa Fabric
WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE
181769 | KAZEN-MAEBASI-397 | CNJ2 | 239345 |  | 10-Jan-24 |  | -7 | KAIN OK | 181849 | ADIDAS | GM1 | 290062 | PUTRI EGA ANJELIA | 11-Jan-24 |  | -6 | 0 | 181778 | KAZEN-S#SENDAI-393 | CNJ2 | 235077 | GITA | 61 | 59 | -3.28 |  | 181838 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.366 | 0.3182 | -13.06 | 181621 | ADIDAS | GM1 | 292582 | PUTRI EGA ANJELIA | -44.45 | 16 February | 181434 | SKECHERS-S# | CVA | 294602 | NOFITA CICILIA | 0.11 | 07 February
181744 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 12-Jan-24 |  | -5 | 0 | 181849 | ADIDAS | GM1 | 290063 | PUTRI EGA ANJELIA | 11-Jan-24 |  | -6 | 0 | 181781 | KAZEN-URAYASU-393 | CNJ2 | 235077 |  | 61 | 59 | -3.28 |  | 181781 | KAZEN-URAYASU-393 | CNJ2 | 235077 |  | 0.2268 | 0.2 | -11.82 | 181834 | ADIDAS | GM2 | 292107 | RESTY HERMA ROSTANIKA | -31.75 | 15 March | 181711 | ADIDAS | GK | 292101 | TRI LESTARI | 0.22 | 01 March
181745 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 12-Jan-24 |  | -5 | 0 | 181849 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 11-Jan-24 |  | -6 | 0 | 181711 | ADIDAS | GK | 292100 | SUMIATI | 58 | 58.2 | 0.28 |  | 181621 | ADIDAS | GM1 | 292582 | PUTRI EGA ANJELIA | 0.431 | 0.4081 | -5.31 | 181830 | ADIDAS | GM1 | 292100 | PUTRI EGA ANJELIA | -12.06 | 15 March | 181711 | ADIDAS | GK | 290061 | TRI LESTARI | 0.3 | 01 March
181745 | ADIDAS | GM1 | 292101 | PUTRI EGA ANJELIA | 12-Jan-24 |  | -5 | 0 | 181849 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 11-Jan-24 |  | -6 | 0 | 181711 | ADIDAS | GK | 290061 | SUMIATI | 58 | 58.2 | 0.28 |  | 181621 | ADIDAS | GM1 | 292578 | PUTRI EGA ANJELIA | 0.419 | 0.4096 | -2.24 | 181756 | KAZEN-S# | CNJ2 | 247754 |  | -11.91 | 15 March | 181430 | SKECHERS-S# | CVA | 294598 | NOFITA CICILIA | 0.42 | 07 February
181745 | ADIDAS | GM1 | 295060 | PUTRI EGA ANJELIA | 12-Jan-24 |  | -5 | 0 | 181840 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181711 | ADIDAS | GK | 292101 | SUMIATI | 58 | 58.2 | 0.28 |  | 181825 | ADIDAS | GK | 290059 | TRI LESTARI | 0.335 | 0.3313 | -1.1 | 181836 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | -8.46 | 15 March | 181825 | ADIDAS | GK | 290059 | TRI LESTARI | 0.57 | 15 March
181746 | ADIDAS | GM2 | 292119 | RESTY HERMA ROSTANIKA | 12-Jan-24 |  | -5 | KAIN BLM RCVD | 181840 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181712 | ADIDAS | GK | 292100 | SUMIATI | 58 | 58.2 | 0.28 |  | 181711 | ADIDAS | GK | 292100 | TRI LESTARI | 0.332 | 0.3285 | -1.05 | 181836 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | -8.35 | 15 March | 181432 | SKECHERS-S# | CVA | 294601 | NOFITA CICILIA | 0.74 | 07 February
181745 | ADIDAS | GM1 | 292118 | PUTRI EGA ANJELIA | 12-Jan-24 |  | -5 | KAIN BLM RCVD | 181840 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181712 | ADIDAS | GK | 290061 | SUMIATI | 58 | 58.2 | 0.28 |  | 181711 | ADIDAS | GK | 290061 | TRI LESTARI | 0.332 | 0.3285 | -1.05 | 181837 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | -6.5 | 15 March | 181778 | KAZEN-S#SENDAI-393 | CNJ2 | 235077 |  | 1.3 | 22 March
181744 | ADIDAS | GM1 | 292117 | PUTRI EGA ANJELIA | 12-Jan-24 |  | -5 | KAIN BLM RCVD | 181757 | KAZEN-S# | CNJ2 | 260872 |  | 18-Jan-24 |  | 1 | KAIN DI KIRIM HARI INI | 181712 | ADIDAS | GK | 292101 | SUMIATI | 58 | 58.2 | 0.28 |  | 181711 | ADIDAS | GK | 292101 | TRI LESTARI | 0.332 | 0.3285 | -1.05 | 181429 | SKECHERS-S# | CVA | 294597 | NOFITA CICILIA | -6.39 | 07 February | 181781 | KAZEN-URAYASU-393 | CNJ2 | 235077 |  | 1.33 | 23 February
181747 | ADIDAS | GM2 | 292113 | RESTY HERMA ROSTANIKA | 12-Jan-24 |  | -5 | KAIN BLM RCVD | 181824 | ADIDAS | GK | 290059 | TRI LESTARI | 19-Jan-24 |  | 2 | 0 | 181825 | ADIDAS | GK | 290059 | SUMIATI | 58 | 58.2 | 0.28 |  | 181712 | ADIDAS | GK | 292100 | TRI LESTARI | 0.412 | 0.4085 | -0.85 | 181835 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | -6.26 | 15 March | 181712 | ADIDAS | GK | 292101 | TRI LESTARI | 1.5 | 01 March
181840 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181828 | ADIDAS | GK | 290059 | TRI LESTARI | 19-Jan-24 |  | 2 | 0 | 181621 | ADIDAS | GM1 | 292578 | SUMIATI | 58 | 58.2 | 0.34 |  | 181712 | ADIDAS | GK | 290061 | TRI LESTARI | 0.412 | 0.4085 | -0.85 | 181837 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | -6.17 | 15 March | 181429 | SKECHERS-S# | CVA | 294597 | NOFITA CICILIA | 1.52 | 07 February
181846 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 15-Jan-24 |  | -2 | 0 | 181826 | ADIDAS | GK | 290062 | TRI LESTARI | 19-Jan-24 |  | 2 | 0 | 181621 | ADIDAS | GM1 | 292582 | SUMIATI | 58 | 58.6 | 1 |  | 181712 | ADIDAS | GK | 292101 | TRI LESTARI | 0.412 | 0.4085 | -0.85 | 181829 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | -5.95 | 15 March | 181833 | ADIDAS | GM2 | 292101 | RESTY HERMA ROSTANIKA | 2.12 | 15 March
181849 | ADIDAS | GM1 | 290062 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181826 | ADIDAS | GK | 290063 | TRI LESTARI | 19-Jan-24 |  | 2 | 0 | 181430 | SKECHERS-S# | CVA | 294598 | GITA | 62 | 63 | 1.61 |  | 181845 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.183 | 0.1816 | -0.77 | 181837 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | -5.93 | 15 March | 181839 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 2.39 | 15 March
181849 | ADIDAS | GM1 | 290063 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181824 | ADIDAS | GK | 290061 | TRI LESTARI | 19-Jan-24 |  | 2 | 0 | 181431 | SKECHERS-S# | CVA | 294598 | GITA | 62 | 63 | 1.61 |  | 181770 | KAZEN-MAEBASI-C1 | CNJ2 | 239345 |  | 0.1518 | 0.1512 | -0.4 | 181743 | ADIDAS | GM1 | 292116 | PUTRI EGA ANJELIA | -3.05 | 01 March | 181711 | ADIDAS | GK | 292100 | TRI LESTARI | 2.55 | 01 March
181840 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181826 | ADIDAS | GK | 290061 | TRI LESTARI | 19-Jan-24 |  | 2 | 0 | 181432 | SKECHERS-S# | CVA | 294601 | GITA | 62 | 64 | 3.23 |  | 181836 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 0.388 | 0.387 | -0.26 | 181827 | ADIDAS | GK | 290059 | TRI LESTARI | -3 | 15 March | 181712 | ADIDAS | GK | 290061 | TRI LESTARI | 2.57 | 01 March
181849 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181828 | ADIDAS | GK | 290061 | TRI LESTARI | 19-Jan-24 |  | 2 | 0 | 181433 | SKECHERS-S# | CVA | 294601 | GITA | 62 | 64 | 3.23 |  | 181833 | ADIDAS | GM2 | 293262 | RESTY HERMA ROSTANIKA | 0.411 | 0.41 | -0.24 | 181827 | ADIDAS | GK | 290061 | TRI LESTARI | -3 | 15 March | 181839 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 2.84 | 15 March
181830 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181824 | ADIDAS | GK | 290060 | TRI LESTARI | 19-Jan-24 |  | 2 | 0 | 181434 | SKECHERS-S# | CVA | 294602 | GITA | 62 | 64 | 3.23 |  | 181755 | KAZEN-S# | GM1 | 247754 | PUTRI EGA ANJELIA | 0.9336 | 0.9315 | -0.22 | 181838 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | -2.91 | 15 March | 181836 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 2.85 | 15 March
181840 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181828 | ADIDAS | GK | 290060 | TRI LESTARI | 19-Jan-24 |  | 2 | 0 | 181435 | SKECHERS-S# | CVA | 294602 | GITA | 62 | 64 | 3.23 |  | 181835 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.38 | 0.3793 | -0.18 | 181838 | ADIDAS | GM2 | 290063 | RESTY HERMA ROSTANIKA | -2.91 | 15 March | 181833 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 2.95 | 15 March
181849 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181831 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 19-Jan-24 |  | 2 | 0 | 181429 | SKECHERS-S# | CVA | 294597 | GITA | 62 | 64.5 | 4.03 |  | 181836 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 0.388 | 0.3873 | -0.18 | 181838 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | -2.91 | 15 March | 181839 | ADIDAS | GM2 | 290063 | RESTY HERMA ROSTANIKA | 3.22 | 15 March
181830 | ADIDAS | GM1 | 292100 | PUTRI EGA ANJELIA | 15-Jan-24 |  | -2 | 0 | 181831 | ADIDAS | GM1 | 292730 | PUTRI EGA ANJELIA | 19-Jan-24 |  | 2 | 0 | 181428 | SKECHERS-S# | CVA | 294597 | GITA | 62 | 65 | 4.84 |  | 181839 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.462 | 0.4617 | -0.06 | 181827 | ADIDAS | GK | 290060 | TRI LESTARI | -2.91 | 15 March | 181834 | ADIDAS | GM2 | 292101 | RESTY HERMA ROSTANIKA | 3.43 | 15 March
181831 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 16-Jan-24 |  | -1 | 0 | 181831 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 19-Jan-24 |  | 2 | 0 | 181768 | KAZEN-MAEBASI-393 | CNJ2 | 239345 | GITA | 0 | 59 |  | Plan Lebar Kain Tidak Ditemukan | 181839 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 0.462 | 0.4617 | -0.06 | 181712 | ADIDAS | GK | 292100 | TRI LESTARI | -1.04 | 01 March | 181834 | ADIDAS | GM2 | 292107 | RESTY HERMA ROSTANIKA | 4.12 | 15 March
181831 | ADIDAS | GM1 | 292730 | PUTRI EGA ANJELIA | 16-Jan-24 |  | -1 | 0 | 181750 | KAZEN-S# | CNJ2 | 260872 |  | 19-Jan-24 |  | 2 | KAIN DI KIRIM HARI INI | 181770 | KAZEN-MAEBASI-C1 | CNJ2 | 239345 | GITA | 0 | 59 |  | Plan Lebar Kain Tidak Ditemukan | 181839 | ADIDAS | GM2 | 290063 | RESTY HERMA ROSTANIKA | 0.462 | 0.4617 | -0.06 | 181830 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | -0.3 | 15 March | 181834 | ADIDAS | GM2 | 293955 | RESTY HERMA ROSTANIKA | 4.12 | 15 March
181831 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 16-Jan-24 |  | -1 | 0 | 181769 | KAZEN-MAEBASI-397 | CNJ2 | 239345 |  | 20-Jan-24 |  | 3 | KAIN OK | 181769 | KAZEN-MAEBASI-397 | CNJ2 | 239345 | GITA | 0 |  |  | Plan Lebar Kain Tidak Ditemukan | 181833 | ADIDAS | GM2 | 292101 | RESTY HERMA ROSTANIKA | 0.411 | 0.4108 | -0.05 | 181830 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | -0.3 | 15 March | 181428 | SKECHERS-S# | CVA | 294597 | NOFITA CICILIA | 4.27 | 07 February
181750 | KAZEN-S# | CNJ2 | 260872 |  | 16-Jan-24 |  | -1 | KAIN DI KIRIM HARI INI | 181415 | BERGANS, | GM1 | 286125 | PUTRI EGA ANJELIA | 23-Jan-24 |  | 6 | 0 | 181741 | ADIDAS | GM1 | 290059 | SUMIATI | 58 |  |  |  | 181833 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 0.411 | 0.4108 | -0.05 | 181711 | ADIDAS | GK | 292100 | TRI LESTARI | -0.01 | 01 March | 181833 | ADIDAS | GM2 | 293262 | RESTY HERMA ROSTANIKA | 4.58 | 15 March
181757 | KAZEN-S# | CNJ2 | 260872 |  | 17-Jan-24 |  | 0 | KAIN DI KIRIM HARI INI | 181415 | BERGANS, | GM1 | 286304 | PUTRI EGA ANJELIA | 23-Jan-24 |  | 6 | 0 | 181742 | ADIDAS | GM1 | 290059 | SUMIATI | 58 |  |  |  | 181836 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.388 | 0.3878 | -0.05 | 181415 | BERGANS, | GM1 | 286125 | PUTRI EGA ANJELIA | 0.12 | 15 March | 181836 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 4.6 | 15 March
181752 | KAZEN-S# | CNJ2 | 254292 |  | 17-Jan-24 |  | 0 | KAIN KIRIM PARTIAL, PLAN CUT TANGGAL 29 JANUARI 2024 | 181415 | BERGANS, | GM1 | 293565 | PUTRI EGA ANJELIA | 23-Jan-24 |  | 6 | 0 | 181743 | ADIDAS | GM1 | 290059 | SUMIATI | 58 |  |  |  | 181838 | ADIDAS | GM2 | 290063 | RESTY HERMA ROSTANIKA | 0.366 | 0.3661 | 0.03 | 181428 | SKECHERS-S# | CVA | 294597 | NOFITA CICILIA | 3.63 | 07 February | 181621 | ADIDAS | GM1 | 292578 | PUTRI EGA ANJELIA | 5.46 | 16 February
[9 empty] | 181741 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 24-Jan-24 |  | 7 | 0 | 181743 | ADIDAS | GM1 | 290061 | SUMIATI | 58 |  |  |  | 181768 | KAZEN-MAEBASI-393 | CNJ2 | 239345 |  | 0.1984 | 0.1985 | 0.05 | 181434 | SKECHERS-S# | CVA | 294602 | NOFITA CICILIA | 147.87 | 07 February | 181744 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 6.73 | 01 March
[9 empty] | 181743 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 24-Jan-24 |  | 7 | 0 | 181743 | ADIDAS | GM1 | 290060 | SUMIATI | 58 |  |  |  | 181832 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 0.326 | 0.3263 | 0.09 | 181432 | SKECHERS-S# | CVA | 294601 | NOFITA CICILIA | 150.51 | 07 February | 181768 | KAZEN-MAEBASI-393 | CNJ2 | 239345 |  | 6.99 | 22 March
[9 empty] | 181743 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 24-Jan-24 |  | 7 | 0 | 181744 | ADIDAS | GM1 | 292117 | SUMIATI | 58 |  |  |  | 181834 | ADIDAS | GM2 | 292101 | RESTY HERMA ROSTANIKA | 0.331 | 0.3313 | 0.09 | 181430 | SKECHERS-S# | CVA | 294598 | NOFITA CICILIA | 155.35 | 07 February | 181743 | ADIDAS | GM1 | 292116 | PUTRI EGA ANJELIA | 7.1 | 01 March
[9 empty] | 181743 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 24-Jan-24 |  | 7 | 0 | 181744 | ADIDAS | GM1 | 290059 | SUMIATI | 58 |  |  |  | 181832 | ADIDAS | GM2 | 293262 | RESTY HERMA ROSTANIKA | 0.326 | 0.3264 | 0.12 | [7 empty] | 181712 | ADIDAS | GK | 292100 | TRI LESTARI | 7.54 | 01 March
[9 empty] | 181827 | ADIDAS | GK | 290059 | TRI LESTARI | 24-Jan-24 |  | 7 | 0 | 181744 | ADIDAS | GM1 | 290061 | SUMIATI | 58 |  |  |  | 181834 | ADIDAS | GM2 | 293955 | RESTY HERMA ROSTANIKA | 0.331 | 0.3314 | 0.12 | [7 empty] | 181838 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 7.8 | 15 March
[9 empty] | 181827 | ADIDAS | GK | 290061 | TRI LESTARI | 24-Jan-24 |  | 7 | 0 | 181746 | ADIDAS | GM2 | 292119 | SUMIATI | 58 |  |  |  | 181838 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 0.366 | 0.3665 | 0.14 | [7 empty] | 181835 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 8.86 | 15 March
[9 empty] | 181827 | ADIDAS | GK | 290060 | TRI LESTARI | 24-Jan-24 |  | 7 | 0 | 181746 | ADIDAS | GM2 | 290059 | SUMIATI | 58 |  |  |  | 181832 | ADIDAS | GM2 | 292101 | RESTY HERMA ROSTANIKA | 0.326 | 0.3265 | 0.15 | [7 empty] | 181837 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 10.06 | 15 March
[9 empty] | 181746 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 26-Jan-24 |  | 9 | 0 | 181746 | ADIDAS | GM2 | 292105 | SUMIATI | 58 |  |  |  | 181837 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | 0.38 | 0.388 | 2.11 | [7 empty] | 181621 | ADIDAS | GM1 | 292582 | PUTRI EGA ANJELIA | 10.12 | 16 February
[9 empty] | 181746 | ADIDAS | GM2 | 292105 | RESTY HERMA ROSTANIKA | 26-Jan-24 |  | 9 | 0 | 181746 | ADIDAS | GM2 | 290061 | SUMIATI | 58 |  |  |  | 181837 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 0.38 | 0.388 | 2.11 | [7 empty] | 181838 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 11.19 | 15 March
[9 empty] | 181746 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 26-Jan-24 |  | 9 | 0 | 181745 | ADIDAS | GM1 | 292118 | SUMIATI | 58 |  |  |  | 181837 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 0.38 | 0.388 | 2.11 | [7 empty] | 181832 | ADIDAS | GM2 | 293262 | RESTY HERMA ROSTANIKA | 11.39 | 15 March
[9 empty] | 181746 | ADIDAS | GM2 | 292119 | RESTY HERMA ROSTANIKA | 26-Jan-24 |  | 9 | KAIN BLM RCVD | 181745 | ADIDAS | GM1 | 290061 | SUMIATI | 58 |  |  |  | 181778 | KAZEN-S#SENDAI-393 | CNJ2 | 235077 |  | 0.2176 | 0.2222 | 2.11 | [7 empty] | 181755 | KAZEN-S# | GM1 | 247754 | PUTRI EGA ANJELIA | 11.47 | 15 March
[9 empty] | 181742 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 29-Jan-24 |  | 12 | 0 | 181745 | ADIDAS | GM1 | 292101 | SUMIATI | 58 |  |  |  | 181740 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 0.197 | 0.294 | 49.24 | [7 empty] | 181837 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | 12.62 | 15 March
[9 empty] | 181752 | KAZEN-S# | CNJ2 | 254292 |  | 29-Jan-24 |  | 12 | KAIN KIRIM PARTIAL, PLAN CUT TANGGAL 29 JANUARI 2024 | 181745 | ADIDAS | GM1 | 295060 | SUMIATI | 58 |  |  |  | 181742 | ADIDAS | GM1 | 292099 | PUTRI EGA ANJELIA | 0.197 | 0.294 | 49.24 | [7 empty] | 181838 | ADIDAS | GM2 | 290063 | RESTY HERMA ROSTANIKA | 14.94 | 15 March
[9 empty] | 181748 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 31-Jan-24 |  | 14 | 0 | 181747 | ADIDAS | GM2 | 292113 | SUMIATI | 58 |  |  |  | 181742 | ADIDAS | GM1 | 292105 | PUTRI EGA ANJELIA | 0.197 | 0.294 | 49.24 | [7 empty] | 181832 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 15.06 | 15 March
[9 empty] | 181745 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 31-Jan-24 |  | 14 | 0 | 181747 | ADIDAS | GM2 | 292121 | SUMIATI | 58 |  |  |  | 181742 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 0.197 | 0.294 | 49.24 | [7 empty] | 181832 | ADIDAS | GM2 | 292101 | RESTY HERMA ROSTANIKA | 16.23 | 15 March
[9 empty] | 181745 | ADIDAS | GM1 | 292101 | PUTRI EGA ANJELIA | 31-Jan-24 |  | 14 | 0 | 181747 | ADIDAS | GM2 | 290059 | SUMIATI | 58 |  |  |  | 181743 | ADIDAS | GM1 | 292116 | PUTRI EGA ANJELIA | 0.197 | 0.294 | 49.24 | [7 empty] | 181837 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 19.46 | 15 March
[9 empty] | 181745 | ADIDAS | GM1 | 295060 | PUTRI EGA ANJELIA | 31-Jan-24 |  | 14 | 0 | 181747 | ADIDAS | GM2 | 290060 | SUMIATI | 58 |  |  |  | 181744 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 0.197 | 0.294 | 49.24 | [7 empty] | 181770 | KAZEN-MAEBASI-C1 | CNJ2 | 239345 |  | 26.46 | 22 March
[9 empty] | 181745 | ADIDAS | GM1 | 292118 | PUTRI EGA ANJELIA | 31-Jan-24 |  | 14 | KAIN BLM RCVD | 181748 | ADIDAS | GM2 | 290059 | SUMIATI | 58 |  |  |  | 181432 | SKECHERS-S# | CVA | 294601 | NOFITA CICILIA | 0.762 | 27.3333 | 3487.05 | [7 empty] | 181742 | ADIDAS | GM1 | 292105 | PUTRI EGA ANJELIA | 37.23 | 01 March
[9 empty] | 181747 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 02-Feb-24 |  | 16 | 0 | 181749 | ADIDAS | GM2 | 292116 | SUMIATI | 58 |  |  |  | 181434 | SKECHERS-S# | CVA | 294602 | NOFITA CICILIA | 0.762 | 27.3333 | 3487.05 | [7 empty] | 181742 | ADIDAS | GM1 | 292099 | PUTRI EGA ANJELIA | 39.33 | 01 March
[9 empty] | 181747 | ADIDAS | GM2 | 292121 | RESTY HERMA ROSTANIKA | 02-Feb-24 |  | 16 | 0 | 181749 | ADIDAS | GM2 | 290059 | SUMIATI | 58 |  |  |  | 181433 | SKECHERS-S# | CVA | 294601 | NOFITA CICILIA | 0.761 | 27.3333 | 3491.76 | [7 empty] | 181742 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 76.64 | 01 March
[9 empty] | 181747 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 02-Feb-24 |  | 16 | 0 | 181749 | ADIDAS | GM2 | 290061 | SUMIATI | 58 |  |  |  | 181435 | SKECHERS-S# | CVA | 294602 | NOFITA CICILIA | 0.761 | 27.3333 | 3491.76
[9 empty] | 181747 | ADIDAS | GM2 | 292113 | RESTY HERMA ROSTANIKA | 02-Feb-24 |  | 16 | KAIN BLM RCVD | 181749 | ADIDAS | GM2 | 290060 | SUMIATI | 58 |  |  |  | 181430 | SKECHERS-S# | CVA | 294598 | NOFITA CICILIA | 0.751 | 27 | 3495.21
[9 empty] | 181749 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 07-Feb-24 |  | 21 | 0 | 181756 | KAZEN-S# | CNJ2 | 247754 |  | 59 |  |  |  | 181431 | SKECHERS-S# | CVA | 294598 | NOFITA CICILIA | 0.749 | 27 | 3504.81
[9 empty] | 181749 | ADIDAS | GM2 | 292116 | RESTY HERMA ROSTANIKA | 07-Feb-24 |  | 21 | 0 | 181415 | BERGANS, | GM1 | 293565 |  | 50 |  |  |  | 181429 | SKECHERS-S# | CVA | 294597 | NOFITA CICILIA | 0.723 | 26.1667 | 3519.18
[9 empty] | 181749 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 07-Feb-24 |  | 21 | 0 | 181415 | BERGANS, | GM1 | 286304 |  | 50 |  |  |  | 181428 | SKECHERS-S# | CVA | 294597 | NOFITA CICILIA | 0.723 | 26.1667 | 3519.18
[9 empty] | 181749 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 07-Feb-24 |  | 21 | 0 | 181415 | BERGANS, | GM1 | 286125 |  | 50
[9 empty] | 181841 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 07-Feb-24 |  | 21 | 0 | 181824 | ADIDAS | GK | 290060 | SUMIATI | 58
[9 empty] | 181841 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 07-Feb-24 |  | 21 | 0 | 181824 | ADIDAS | GK | 290059 | SUMIATI | 58
[9 empty] | 181841 | ADIDAS | GM2 | 292100 | RESTY HERMA ROSTANIKA | 07-Feb-24 |  | 21 | 0 | 181824 | ADIDAS | GK | 290061 | SUMIATI | 58
[9 empty] | 181841 | ADIDAS | GM2 | 294353 | RESTY HERMA ROSTANIKA | 07-Feb-24 |  | 21 | 0 | 181826 | ADIDAS | GK | 290062 | SUMIATI | 58
[9 empty] | 181842 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 08-Feb-24 |  | 22 | 0 | 181826 | ADIDAS | GK | 290061 | SUMIATI | 58
[9 empty] | 181842 | ADIDAS | GM2 | 292103 | RESTY HERMA ROSTANIKA | 08-Feb-24 |  | 22 | 0 | 181826 | ADIDAS | GK | 290063 | SUMIATI | 58
[9 empty] | 181842 | ADIDAS | GM2 | 293266 | RESTY HERMA ROSTANIKA | 08-Feb-24 |  | 22 | 0 | 181827 | ADIDAS | GK | 290060 | SUMIATI | 58
[9 empty] | 181842 | ADIDAS | GM2 | 293267 | RESTY HERMA ROSTANIKA | 08-Feb-24 |  | 22 | 0 | 181827 | ADIDAS | GK | 290059 | SUMIATI | 58
[9 empty] | 181744 | ADIDAS | GM1 | 290061 | PUTRI EGA ANJELIA | 13-Feb-24 |  | 27 | 0 | 181827 | ADIDAS | GK | 290061 | SUMIATI | 58
[9 empty] | 181744 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 13-Feb-24 |  | 27 | 0 | 181828 | ADIDAS | GK | 290060 | SUMIATI | 58
[9 empty] | 181744 | ADIDAS | GM1 | 292117 | PUTRI EGA ANJELIA | 13-Feb-24 |  | 27 | KAIN BLM RCVD | 181828 | ADIDAS | GK | 290059 | SUMIATI | 58
[9 empty] | 181843 | ADIDAS | GM2 | 292099 | RESTY HERMA ROSTANIKA | 16-Feb-24 |  | 30 | 0 | 181828 | ADIDAS | GK | 290061 | SUMIATI | 58
[9 empty] | 181843 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 16-Feb-24 |  | 30 | 0 | 181842 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[9 empty] | 181843 | ADIDAS | GM2 | 292101 | RESTY HERMA ROSTANIKA | 16-Feb-24 |  | 30 | 0 | 181842 | ADIDAS | GM2 | 293266 | SUMIATI | 58
[9 empty] | 181843 | ADIDAS | GM2 | 293268 | RESTY HERMA ROSTANIKA | 16-Feb-24 |  | 30 | 0 | 181842 | ADIDAS | GM2 | 292103 | SUMIATI | 58
[9 empty] | 181844 | ADIDAS | GM2 | 293956 | RESTY HERMA ROSTANIKA | 19-Feb-24 |  | 33 | 0 | 181842 | ADIDAS | GM2 | 293267 | SUMIATI | 58
[9 empty] | 181844 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 19-Feb-24 |  | 33 | 0 | 181847 | ADIDAS | GM2 | 290064 | SUMIATI | 58
[9 empty] | 181844 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 19-Feb-24 |  | 33 | 0 | 181847 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[9 empty] | 181844 | ADIDAS | GM2 | 293957 | RESTY HERMA ROSTANIKA | 19-Feb-24 |  | 33 | 0 | 181847 | ADIDAS | GM2 | 290060 | SUMIATI | 58
[9 empty] | 181846 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 20-Feb-24 |  | 34 | 0 | 181847 | ADIDAS | GM2 | 290061 | SUMIATI | 58
[9 empty] | 181756 | KAZEN-S# | CNJ2 | 247754 |  | 23-Feb-24 |  | 37 | KAIN OK | 181830 | ADIDAS | GM1 | 290059 | SUMIATI | 58
[9 empty] | 181847 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 29-Feb-24 |  | 43 | 0 | 181830 | ADIDAS | GM1 | 292100 | SUMIATI | 58
[9 empty] | 181847 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 29-Feb-24 |  | 43 | 0 | 181830 | ADIDAS | GM1 | 290060 | SUMIATI | 58
[9 empty] | 181847 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 29-Feb-24 |  | 43 | 0 | 181840 | ADIDAS | GM1 | 290060 | SUMIATI | 58
[9 empty] | 181847 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | 29-Feb-24 |  | 43 | 0 | 181840 | ADIDAS | GM1 | 290059 | SUMIATI | 58
[9 empty] | 181848 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 05-Mar-24 |  | 48 | 0 | 181840 | ADIDAS | GM1 | 290061 | SUMIATI | 58
[9 empty] | 181848 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 05-Mar-24 |  | 48 | 0 | 181849 | ADIDAS | GM1 | 290062 | SUMIATI | 58
[9 empty] | 181848 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 05-Mar-24 |  | 48 | 0 | 181849 | ADIDAS | GM1 | 290061 | SUMIATI | 58
[9 empty] | 181848 | ADIDAS | GM2 | 292735 | RESTY HERMA ROSTANIKA | 05-Mar-24 |  | 48 | 0 | 181849 | ADIDAS | GM1 | 290063 | SUMIATI | 58
[9 empty] | 181829 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 19-Apr-24 |  | 93 | 0 | 181849 | ADIDAS | GM1 | 290060 | SUMIATI | 58
[9 empty] | 181830 | ADIDAS | GM1 | 290059 | PUTRI EGA ANJELIA | 22-Apr-24 |  | 96 | 0 | 181841 | ADIDAS | GM2 | 290060 | SUMIATI | 58
[9 empty] | 181830 | ADIDAS | GM1 | 290060 | PUTRI EGA ANJELIA | 22-Apr-24 |  | 96 | 0 | 181841 | ADIDAS | GM2 | 292100 | SUMIATI | 58
[9 empty] | 181830 | ADIDAS | GM1 | 292100 | PUTRI EGA ANJELIA | 22-Apr-24 |  | 96 | 0 | 181841 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[18 empty] | 181841 | ADIDAS | GM2 | 294353 | SUMIATI | 58
[18 empty] | 181843 | ADIDAS | GM2 | 292099 | SUMIATI | 58
[18 empty] | 181843 | ADIDAS | GM2 | 292101 | SUMIATI | 58
[18 empty] | 181843 | ADIDAS | GM2 | 290061 | SUMIATI | 58
[18 empty] | 181843 | ADIDAS | GM2 | 293268 | SUMIATI | 58
[18 empty] | 181844 | ADIDAS | GM2 | 293956 | SUMIATI | 58
[18 empty] | 181844 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[18 empty] | 181844 | ADIDAS | GM2 | 290060 | SUMIATI | 58
[18 empty] | 181844 | ADIDAS | GM2 | 293957 | SUMIATI | 58
[18 empty] | 181846 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[18 empty] | 181848 | ADIDAS | GM2 | 292735 | SUMIATI | 58
[18 empty] | 181848 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[18 empty] | 181848 | ADIDAS | GM2 | 290060 | SUMIATI | 58
[18 empty] | 181848 | ADIDAS | GM2 | 290061 | SUMIATI | 58
[18 empty] | 181831 | ADIDAS | GM1 | 292730 | SUMIATI | 58
[18 empty] | 181831 | ADIDAS | GM1 | 290061 | SUMIATI | 58
[18 empty] | 181831 | ADIDAS | GM1 | 290059 | SUMIATI | 58
[18 empty] | 181750 | KAZEN-S# | CNJ2 | 260872 |  | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181752 | KAZEN-S# | CNJ2 | 254292 |  | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181757 | KAZEN-S# | CNJ2 | 260872 |  | 0 |  |  | Plan Lebar Kain Tidak Ditemukan
[18 empty] | 181829 | ADIDAS | GM1 | 290059 | SUMIATI | 58