## REPORT HASIL
Co Date vs Fabric Receipt in Cutting Date | [8 empty] | Start Cutting Date vs PPIC Date | [8 empty] | Lebar Kain Plan vs Lebar Kain Actual | [8 empty] | Consumption Plan vs Consumption Actual | [7 empty] | Garment Short/Over (Pcs) | [6 empty] | Sisa Fabric
WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | Pending Day | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | REMARKS | WO | BUYER | BRANCH | ITEM | PIC | PLAN | ACTUAL | % Diff | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE | WO | BUYER | BRANCH | ITEM | PIC | % Diff | SHIP DATE
181865 | NISHIMATSUYA, | CVA | 287317 | NOFITA CICILIA | 12-Feb-24 |  | -4 | plan cutting di tanggal 21/02,PLAN DATANG KAIN 13/02 PARTIAL | 181865 | NISHIMATSUYA, | CVA | 287403 | NOFITA CICILIA | 09-Feb-24 |  | -7 | plan cutting di tanggal 21/02,PLAN DATANG KAIN 13/02 PARTIAL | 181865 | NISHIMATSUYA, | CVA | 287318 | GITA | 42 | 42.5 | 1.16 |  | 181865 | NISHIMATSUYA, | CVA | 287318 | NOFITA CICILIA | 0.071 | 0.0692 | -2.54 | 181865 | NISHIMATSUYA, | CVA | 287317 | NOFITA CICILIA | -20.69 | 22 April | 181865 | NISHIMATSUYA, | CVA | 287319 | NOFITA CICILIA | 1.4 | 22 April
[9 empty] | 181865 | NISHIMATSUYA, | CVA | 287317 | NOFITA CICILIA | 09-Feb-24 |  | -7 | plan cutting di tanggal 21/02,PLAN DATANG KAIN 13/02 PARTIAL | 181865 | NISHIMATSUYA, | CVA | 287319 | GITA | 42 | 43 | 2.38 |  | 181999 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | 0.34 | 0.3378 | -0.65 | 181865 | NISHIMATSUYA, | CVA | 287318 | NOFITA CICILIA | -2.94 | 22 April | 181865 | NISHIMATSUYA, | CVA | 287318 | NOFITA CICILIA | 3.35 | 22 April
[9 empty] | 182001 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 03-Mar-24 |  | 16 |  | 181865 | NISHIMATSUYA, | CVA | 287403 | GITA | 42 |  |  |  | 181440 | SKECHERS-S# | CVA | 294609 | NOFITA CICILIA | 0.958 | 0.9646 | 0.69 | 181865 | NISHIMATSUYA, | CVA | 287319 | NOFITA CICILIA | -2.27 | 22 April | 181440 | SKECHERS-S# | CVA | 294609 | NOFITA CICILIA | 6.14 | 19 February
[9 empty] | 181999 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 12-Mar-24 |  | 25 |  | 181865 | NISHIMATSUYA, | CVA | 287317 | GITA | 42 |  |  |  | 181441 | SKECHERS-S# | CVA | 294609 | NOFITA CICILIA | 0.957 | 0.9646 | 0.79 | 182001 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | -0.23 | 15 March | 181999 | ADIDAS | GM2 | 290064 | RESTY HERMA ROSTANIKA | 6.41 | 15 March
[9 empty] | 181999 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 12-Mar-24 |  | 25 |  | 181999 | ADIDAS | GM2 | 290060 | SUMIATI | 58 |  |  |  | 181865 | NISHIMATSUYA, | CVA | 287319 | NOFITA CICILIA | 0.07 | 0.0706 | 0.86 | 181865 | NISHIMATSUYA, | CVA | 287403 | NOFITA CICILIA | -0.19 | 22 April | 181441 | SKECHERS-S# | CVA | 294609 | NOFITA CICILIA | 10.3 | 19 February
[9 empty] | 181999 | ADIDAS | GM2 | 290060 | RESTY HERMA ROSTANIKA | 12-Mar-24 |  | 25 |  | 181999 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[9 empty] | 182000 | ADIDAS | GM2 | 290059 | RESTY HERMA ROSTANIKA | 14-Mar-24 |  | 27 |  | 181999 | ADIDAS | GM2 | 290061 | SUMIATI | 58
[9 empty] | 182003 | ADIDAS | GM2 | 290062 | RESTY HERMA ROSTANIKA | 14-Mar-24 |  | 27 |  | 182000 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[9 empty] | 182003 | ADIDAS | GM2 | 290063 | RESTY HERMA ROSTANIKA | 14-Mar-24 |  | 27 |  | 182001 | ADIDAS | GM2 | 290059 | SUMIATI | 58
[9 empty] | 182003 | ADIDAS | GM2 | 290061 | RESTY HERMA ROSTANIKA | 14-Mar-24 |  | 27 |  | 182003 | ADIDAS | GM2 | 290062 | SUMIATI | 58
[18 empty] | 182003 | ADIDAS | GM2 | 290061 | SUMIATI | 58
[18 empty] | 182003 | ADIDAS | GM2 | 290063 | SUMIATI | 58